## Sheet1
POSITION | PROCESS MAP NAME | ACTIVITY NUMBER | ACTIVITY DISCRIPTION
Senior Management Team | 1.1 Engage with Client | 1 | Identify the Municipality by conducting a workshop 1.1.1
Chief Director | 1.1 Engage with Client | 2 | Table the list of Municipalities with the Planning Director
|  | 5 | Review and Sign
Project Director | 1.1 Engage with Client | 3 | Allocate Municipalities to Project Manager using the Resource Allocation Matrix
|  | 9 | Conduct the meeting (ENGAGE 1)
|  | 15 | Conduct the meeting (ENGAGE 2)
Project Manager | 1.1 Engage with Client | 4 | Draft letter of introduction
|  | 6 | Issue signed Letter to Municipality
|  | 8 | Conduct meeting preparation (ENGAGE 1)
|  | 9 | Conduct the meeting (ENGAGE 1)
|  | 11 | Update the List of Municipalities (If Required)
|  | 12 | Set-up meeting (ENGAGE 2)
|  | 14 | Conduct meeting preparation (ENGAGE 2)
|  | 15 | Conduct the meeting (ENGAGE 2)
Municipality Manager | 1.1 Engage with Client | 7 | Acknowledgment receipt and allocation
Municipal Co-ordinator | 1.1 Engage with Client | 10 | Submit the Steering Committee Details
|  | 13 | Acknowledge Receipt
Municipal Co-ordinator | 1.2 Establish Work Plan | 1 | Draft Work Plan 1.2.2
|  | 3 | Review and Amend
Project Manager | 1.2 Establish Work Plan | 2 | Review draft work plan internally and add comments
|  | 4 | Review and Sign the Work Plan 1.2.2
Project Director | 1.2 Establish Work Plan | 4 | Review and Sign the Work Plan 1.2.2
Municipal Co-ordinator | 1.3 Identifing the Urban Network Elements | 1 | Identify Urban Network elements 1.3.1
Project Manager | 1.3 Identifing the Urban Network Elements | 2 | Acknowledgment Receipt
|  | 3 | Conduct Meeting Preparation
|  | 4 | Conduct meeting 1.3.2
|  | 5 | Initiate meeting with the Municipal Co-ordinator
|  | 6 | Compile Change Request
|  | 7 | Compile Letter of 'No Objection'
Project Director | 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
|  | 8 | Review & Sign Change Request
|  | 9 | Review & Sign the letter of No Objection
Chief Director | 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
|  | 8 | Review & Sign Change Request
|  | 9 | Review & Sign the letter of No Objection
Strategy Specialist | 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
Municipal Co-ordinator | 1.4 Conclude Contractual Arrangements | 1 | Prepare the documents to the council 1.4.1
|  | 4 | Process & the sign the Memorandum of Agreement
Council | 1.4 Conclude Contractual Arrangements | 2 | Review & Approve the Supporting Documents 1.4.2
Project Manager | 1.4 Conclude Contractual Arrangements | 3 | Check and File
|  | 6 | Review, File & Forward a copy of the Memorandum of Agreement to the Municipal Co-ordinator
Chief Director | 1.4 Conclude Contractual Arrangements | 5 | Review & Sign the Memorandum of Agreement 1.4.3
Project Manager | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 1 | Compile Terms of Reference and Professional Service Provider (PSP ) Guidelines 1.5.1
|  | 4 | Schedule a Briefing Session with the Consultant 1.5.3
|  | 6 | Prepare and Chair the Briefing Session 1.5.3
|  | 9 | Review & Approve 1.5.5
Municipal Co-ordinator | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 2 | Add municipal information and start procurement 1.5.2
|  | 3 | Issue a Service Level Agreement 1.5.2
|  | 5 | Arrange the Briefing Session
|  | 8 | Co-ordinate the update of the Work Plan 1.5.4
Technical Adviser Consultant | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 7 | Review & Update the Work Plan
Project Director | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5
Financial Director | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5
Chief Director | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5