## Sheet2
POSITION | PROCESS MAP NAME | ACTIVITY NUMBER | ACTIVITY DISCRIPTION
Senior Management Team | 1.1 Engage with Client | 1 | Identify the Municipality by conducting a workshop 1.1.1
Chief Director | 1.1 Engage with Client | 2 | Table the list of Municipalities with the Planning Director
|  | 5 | Review and Sign
| 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
|  | 8 | Review & Sign Change Request
|  | 9 | Review & Sign the letter of No Objection
| 1.4 Conclude Contractual Arrangements | 5 | Review & Sign the Memorandum of Agreement 1.4.3
| 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5
| Budget Input CG | 7 | Review and Accept
| Budget Input TA | 8 | Review and Accept
| CG Draw Down | 12 | Review and sign the Withholding Letter
| Invoice TA | 14 | Review and approve
|  | 16 | Sign invoice payments batch summary sheet Scan and forward the batch to the financial service provider
Project Director | 1.1 Engage with Client | 3 | Allocate Municipalities to Project Manager using the Resource Allocation Matrix
|  | 9 | Conduct the meeting (ENGAGE 1)
|  | 15 | Conduct the meeting (ENGAGE 2)
| 1.2 Establish Work Plan | 4 | Review and Sign the Work Plan 1.2.2
| 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
|  | 8 | Review & Sign Change Request
|  | 9 | Review & Sign the letter of No Objection
| 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5
| CG Draw Down | 4 | Approves/ rejects the planned CG draw down for the applicable month.
|  | 5 | Provides reason for rejection
|  | 7 | Approves the schedule with comments
|  | 8 | Rejected drawdowns
|  | 9 | Compiles withholding letter and forward to Specialist Finance
| Invoice TA | 12 | Final recommendation of the requirements to approve the invoice.
| Retain Unspent Municipal Funds | 2 | Sends retention memo to all applicable municipalities
|  | 5 | take note of the requests for future drawdowns and communicates any anomalies to the Finance Specialist / Chief Director
|  | 8 | Follow-up and feedback
Project Manager | 1.1 Engage with Client | 4 | Draft letter of introduction
|  | 6 | Issue signed Letter to Municipality
|  | 8 | Conduct meeting preparation (ENGAGE 1)
|  | 9 | Conduct the meeting (ENGAGE 1)
|  | 11 | Update the List of Municipalities (If Required)
|  | 12 | Set-up meeting (ENGAGE 2)
|  | 14 | Conduct meeting preparation (ENGAGE 2)
|  | 15 | Conduct the meeting (ENGAGE 2)
| 1.2 Establish Work Plan | 2 | Review draft work plan internally and add comments
|  | 4 | Review and Sign the Work Plan 1.2.2
| 1.3 Identifing the Urban Network Elements | 2 | Acknowledgment Receipt
|  | 3 | Conduct Meeting Preparation
|  | 4 | Conduct meeting 1.3.2
|  | 5 | Initiate meeting with the Municipal Co-ordinator
|  | 6 | Compile Change Request
|  | 7 | Compile Letter of 'No Objection'
| 1.4 Conclude Contractual Arrangements | 3 | Check and File
|  | 6 | Review, File & Forward a copy of the Memorandum of Agreement to the Municipal Co-ordinator
| 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 1 | Compile Terms of Reference and Professional Service Provider (PSP ) Guidelines 1.5.1
|  | 4 | Schedule a Briefing Session with the Consultant 1.5.3
|  | 6 | Prepare and Chair the Briefing Session 1.5.3
|  | 9 | Review & Approve 1.5.5
| CG Draw Down | 2 | Review and file
| Invoice TA | 9 | Verify that all the required documents are attached and work conducted
|  | 10 | Request more information/ supporting documents
Strategy Specialist | 1.3 Identifing the Urban Network Elements | 4 | Conduct meeting 1.3.2
Technical Adviser Consultant | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 7 | Review & Update the Work Plan
Financial Director | 1.5 Appoint TA Consultant(s), final Work Plan and Funds | 9 | Review & Approve 1.5.5
Financial Specialist | Budget Input CG | 1 | Compile Estimate budget
|  | 2 | Draw MIS Pipeline Report (Predictive)
|  | 3 | Compile Draft Budget
|  | 4 | Engage with the IMPLEMENTATION Director
|  | 5 | Engage with the IMPLEMENTATION Director
|  | 6 | Amend new budget
|  | 8 | Populate on Treasury Template
|  | 9 | Submit the Budget to National Treasury CEO
|  | 11 | Confirm submissions
|  | 12 | File the MTEF Allocation Letter and capture into MIS
|  | 13 | Communicate via e-mail on the Allocation Published (Gazette)
| Budget Input TA | 1 | Review every 6 months
|  | 2 | Compile Estimate budget
|  | 3 | Draw MIS Report (Predictive)
|  | 4 | Compile Draft Budget
|  | 5 | Engage with the Internal Director
|  | 6 | Engage with the Internal Director
|  | 7 | Amend new budget
|  | 9 | Populate on Treasury Template
|  | 10 | Submit the Budget to National Treasury CEO
|  | 12 | Confirm submissions
|  | 13 | File the MTEF Allocation Letter and capture into MIS
|  | 14 | Communicate via e-mail on the Allocation Published (Gazette)
| CG Draw Down | 10 | Prepares an approved drawdown memo to Corp Services.
|  | 11 | Prepares a memo to IGR with the list of intended withholding and attach the withholding letters
|  | 14 | Review (Signatories) and issue to the Project Administrator
|  | 17 | Amends the payment schedule based on the withholding that took place
|  | 18 | Sends approved draw down (final payment instruction) to Corp Services for payment
|  | 19 | Corp Services transfers the funds to the municipalities
|  | 20 | Corp Services sends updated BAS report to NDP Finance
| Payment Schedule CG | 1 | Notify the Municipal Co-ordinator & Technical Advisor to update the Cash flow on MIS
|  | 3 | Draw TA Cash flow Report from MIS
|  | 4 | Compile payment schedule
|  | 5 | Populate the Treasury Payment Schedule
| Payment Schedule TA | 1 | Notify the Municipal Co-ordinator & Technical Advisor to update the Work Plan on MIS
|  | 3 | Draw TA Cash flow Report from MIS
|  | 4 | Compile payment schedule
|  | 5 | Populate the Treasury Payment Schedule
| Retain Unspent Municipal Funds | 1 | Communicates deadlines and workplan to Project Directors.
|  | 4 | Compiles an excel summary report of the requests.
|  | 6 | Compares the submissions to the NDP with the original requests received by the IGR department
|  | 7 | Feedback anomalies to the Project Director
|  | 9 | Submits the NDP view / motivation report to IGR for consideration
|  | 10 | Updates MIS with the returned funds as per the IGR letter
Inplementation Director | Budget Input CG | 7 | Review and Accept
| Budget Input TA | 8 | Review and Accept
National Treasury CEO | Budget Input CG | 10 | Review the Budget and submit to CFO & Functional Group in Treasury
| Budget Input TA | 11 | Review the Budget and submit to CFO & Functional Group in Treasury
NDP Finance | CG Draw Down | 3 | Generates the planned payment schedule for the applicable month.
|  | 6 | Combines all inputs and presents combined view to Chief Director
|  | 21 | Updates the MIS with successful payments
IGR | CG Draw Down | 13 | Review and sign the Withholding Letter
CFO | CG Draw Down | 13 | Review and sign the Withholding Letter
Project Administrator | CG Draw Down | 15 | Fax and email to the affected municipality.
|  | 16 | Compile a Cover of Draw Downs for the month
| Invoice TA | 6 | Upload and link the tax invoice into MIS
|  | 7 | Verify the validity of the claim according to the check list
|  | 7 | Request more information/ supporting documents
|  | 15 | Prepare invoice payment batch summary sheet
Corporate Service | CG Draw Down | 19 | Corp Services transfers the funds to the municipalities
|  | 20 | Corp Services sends updated BAS report to NDP Finance
Team Assistant | Invoice TA | 2 | Acknowledge receipt of Service Provider tax invoice by way of a signature
|  | 3 | Date stamp all documents received from Service Provider
|  | 4 | Record all documents received on the NDPG receipt book
|  | 5 | Scan and save all documents received to the I-drive on the relevant project number
Strategic Support Officer: Finance | Invoice TA | 13 | Verify Validity of the Invoice
Service Provider | Invoice TA | 17 | Final release of tax invoice payments as per invoice payment batch summary sheet
Technical Advisor | Payment Schedule CG | 2 | Update the Cash flow (If Required
| Payment Schedule TA | 2 | Update the Work Plan (If Required)