## Process Flow
1. Programme Initiation
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 1.1 Engage with Client | NDP – PI – 03 - 001 | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
Senior Management Team
Identify the Municipality by conducting a workshop
1.1.1
1
Minutes
1.1.1 (1)
Attendance
Register
File
File Plan
Minutes
1.1.1 (1)
Operations Director
Ensure that the list of municipalities status are updated on MIS
2
NDP Strategy
Urban Planning Director
Allocate Municipalities to Project Manager using the Resource Allocation Matrix
3
Resource Allocation
Matrix
Resource Allocation
Matrix
List of Municipalities
Project Manager
Draft letter of introduction
Letter of Introduction and Meeting Dates
Chief Director
Review and Approve
5
4
O.K.
Yes
No
Meeting Dates
Letter
(Approved)
Project Manager
Issue signed Letter to Municipality
6
Meeting Dates
Letter
(Approved)
Meeting Dates
Letter
(Approved)
Municipality Manager
Acknowledgment receipt and allocation
7
Allocation
- Responsibility
- Meeting dates
Acknowledge
Receipt (E-Mail)
Project Manager
Conduct meeting preparation
(ENGAGE 1)
8
- Presentation
- Material
Agenda
Municipal Co-ordinator
Chief Director & Urban Planning Director
Conduct the meeting
(ENGAGE 1)
9
Minutes
Attendance
Register
Meeting
ENGAGE 1
(Introduction)
- The What
Municipal Co-ordinator
Compile Institutional Arrangements (Draft)
10
Institutional Arrangements
(Draft)
Project Manager
Update the List of Municipalities (Metadata)
(If Required)
11
List of Municipalities
Project Manager
Set-up meeting
(ENGAGE 2)
12
Meeting Dates
Letter
Municipal Co-ordinator
Acknowledge
Receipt
13
Acknowledge
Receipt
Project Manager
Conduct meeting preparation
(ENGAGE 2)
14
- Presentation
- Material (Document Pack)
Agenda
Municipal Co-ordinator
Urban Planning Director & Project Manager
Conduct the meeting
(ENGAGE 2)
15
Meeting
ENGAGE 2
- The How
Institutional arrangements
Municipal Co-ordinator
1.2 Establish Work Plan
MIS
Area For Improvement
New File System / Plan required
MIS
MIS
MIS
Area For Improvement
Toolkit required
MIS
MIS
MIS
MIS
Toolkit
(Urban
Hub Design)
Attendance
Register
Minutes
Example of Council
Resolution
Work Plan
Template
MOA Template
ANALYSIS SHEET
Institutional Arrangements
(Final)
Project Manager
Update the List of Municipalities (Metadata)
(If Required)
16
List of Municipalities
Institutional Arrangements
(Final)
Minutes
Attendance
Register
Area For Improvement
The municipality list (Meta Data) must be verified.
Finance Budget Input process
NDP Strategy process
Finance Specialist
for Budget input
MIS
Automatic notification
to the Planning director
Guidance Note
Area For Improvement
CG (30% cost) criteria must be built into the MOA
MIS
MIS
MIS
Letter of Introduction
File
File Plan
MIS
MIS
File
File Plan
MIS
MIS
MIS
File
File Plan
MIS
File
File Plan
MIS
File
File Plan
MIS
MIS
MIS
File
File Plan
File
File Plan

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 1.1 Engage with Client |  |  | 6.667% |  | 1 | 1 |  | 0 |  | 1 | 2 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recommendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Identify the Municipality Have minutes been recorded and distributed | Approved minutes | [7 empty] | 2 | HIGH | test | dave | 2002-10-30 | OPEN | YES | YES | YES |  |  | 3 | 4 | 1 | 1 | 0 | 1 | 1
2 | Identify the Municipality Have actions, responsible persons and actions dates been included into the minutes | Approved minutes | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Is the list of municipalities status on the MIS current and updated | Current Municipality details on the MIS and allocated to responsible NP Project Manager | [8 empty] | LOW | [9 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0
4 | Has a signed Letter of Introduction been issued and receipt received from the respective Municipality. | Acknowledged receipt on file | [8 empty] | LOW | [9 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0
5 | Are the ENGAGE 1 - THE WHAT meeting minutes on file. Do the indicate actions | Approved minutes on file and MIS updated with Municipality status | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
6 | Are the ENGAGE 2 - THE HOW meeting minutes on file. Do the indicate actions | Approved minutes on file and MIS updated with Municipality status | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
7 | Institutional Arrangements (Final) received from the Municipality Co-ordinator | Institutional Arrangements (Final) on file | [8 empty] | HIGH | [6 empty] | YES | Total number of executive engagements completed |  | 3 | 3 | 0 | 0 | 0 | 0 | 1
8 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
9 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
10 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 2 | [10 empty] | 30 | 23 | 1 | 1 | 0 | 1 | 2
[10 empty] | 46 | [10 empty] | 690

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0