## Process Flow
1. Programme Initiation
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 1.5 Appoint Consultant(s) & finalise work plan & funding | NDP – PI – 03 - 005 | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
Memorandum of Agreement
Work Plan
Project Manager
Compile Terms of Reference and Professional Service Provider (PSP ) Guidelines
1.5.1
1
Terms of Reference
1.5.1 (1)
Professional Service Provider (PSP ) Guidelines
1.5.1 (2)
Municipal Co-ordinator
Add municipal information and start procurement
1.5.2
2
Procurement / Tender Process
Appointed TA Consultant(s)
Municipal Co-ordinator
Issue a Service Level Agreement
1.5.2
3
Service Level
Agreement
1.5.2 (2)
Letter of
Appointment
1.5.2 (1)
Project Manager Schedule a Briefing Session with the Consultant
1.5.3
4
Meeting Dates Letter
Municipal Co-ordinator
Arrange the Briefing Session
5
Acknowledge Receipt
Project Manager & Urban Planning Director
Prepare and Chair the Briefing Session
1.5.3
6
Minutes
Attendance
Register
File
File Plan
Briefing Session conducted
Professional Service Provider (PSP)
Review & Update the Work Plan including cash flow
7
Municipal Co-ordinator
Co-ordinate the update of the Work Plan
1.5.4
8
Updated
Work Plan including cash flow
1.5.4 (1)
Project Manager, Urban Planning Director, Operations Director & Chief Director
Review & Approve
1.5.5
9
O.K.
Yes
No
Approved Work
Plan including cash flow
1.5.5 (1)
MIS
Area For Improvement
Is PSP part of the TOR
MIS
MIS
Guidance
Pack
1.5.3 (1)
Area For Improvement
Approval should be done on MIS
MIS
Municipal Co-ordinator
1.4 Conclude Contractual Arrangements
2.1 Conduct Urban Network Phasing
Finance
Budget Input TA's
ANALYSIS SHEET
Procurement Option
MIS
Area For Improvement
The NDP panel process must be developed
MIS
MIS
Area For Improvement
Workplan must be updated on MIS
Finance
Budget Input TA's
Area For Improvement
Budget pipeline must be discussed.
Area For Improvement
Automatic filling system
Budget Process - Technical Assistance
Activity 3
MIS
NDP panel resources
(DBSA)
MIS
MIS
File
File Plan
MIS
MIS
MIS

## High Level Table
PROGRAMME MANAGEMENT (HIGH-LEVEL PROCESS AND BENEFITS REALISATION)
Management Approach: Urban Network and Precinct Development (Phases, Milestones, Gates, Baselines, Deliverables, Reviews, Audits)
PHASE | 1 Programme Initiation |  |  |  |  | 2 Network Planning |  | 3 Precinct Planning |  |  | 4 Implementation
| 1A | 1B | 1C | 1D | 1E | 2A | 2B | 3A | 3B | 3C | 4A | 4B | 4C | 4D | 4E | 4F
| 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 2.1 | 2.2 | 3.1 | 3.2 | 3.3 | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6
SUBPHASE | Engage with the Client | Establish Work Plan | Identify Urban Network Elements | Conclude Contrcatual Arrangements | Appoint TA Consultant(s) , final Work Plan and Funds | Conduct Urban Network Phasing | UN Order Costing | Conduct Precinct Planning | Conduct Precinct Concept Planning | Listing and Prioritising of NDP Projects | Review / Update Precinct Concept Project Plans | Feasibility / Preliminary Design ( Concept & Viability ) | Detail Design ( Design Development ) | Tender ( Documentation and Procurement ) | Construction ( Contract Administration and Inspection ) | Close-out
MILESTONE |  |  | 1 | 2 |  |  | 3 | 4 | 5 | 6 |  |  | 7 | 8 | 9 | 10
GATES | 1.3: 1; 1.4: 2; 2.2: 3; 3.1: 4; 3.2: 5; 3.3: 6; 4.3: 7; 4.4: 8
BASELINES | 2.2: Urban Network Baseline; 3.2: Precinct Baseline; 4.2: Project Concept Baseline 1; 4.3: Project Tender Baseline 2; 4.4: Project Construction Baseline 3
DELIVERABLES | Minutes of Engagement meetings | Work Plan | UN ID map | Council Submission | Terms of Reference | Urban Network Planning Plan | Updated Network Phasing Plan ( including High Order Costing ) | Precinct Design Plan | Precinct Phasing Plan and Precinct Concept Plan ( Spatial, High Level SDP and Phasing ) | Table of Prioritised Projects ( name, Scope, End Dates, Costing ) | Confirmation of Precinct Scope requirement. | Feasibility Study Reports | Tender Drawings, Documents and Costing from BoA | Contract Award | Delivered Construction Project with AS BUILT Drawings | Close-out Reports
| Institutional arrangement |  | Map description table | Council Resolution | Letter of Appointment |  | NDP Letter of Acceptance | NDP Letter of Acceptance |  |  | Project Execution Plan | Preliminary Design Drawings |  | Final Construction Phase Estimate
|  |  | Letter of NO Objection | MOA for NDP grant | SLA | [5 empty] | Agreement
Consultant Guidance Pack
Updated Work Plan
Approval / Acceptance by NDP | 1.2: Acceptance; 1.3: Letter of NO Objection; 1.4: Signing of MOA for NDP Grant; 1.5: Approval of Updated Work Plan; 2.2: NDP Letter of Acceptance; 3.1: NDP Letter of Acceptance; 3.2: NDP Approval Letter
REVIEWS | 3.2: Precinct Concept Review; 4.2: Preliminary Design review; 4.3: Critical Design Review
AUDITS | 3.1: From 1.3; 3.2: From 2.1; 3.3: From 3.2; 4.3: Functional; 4.5: Physical

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 1.5 Appoint Consultant(s) & finalise work plan & funding |  |  | 0% |  | 0 | 0 |  | 0 |  | 1 | 1 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recommendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | Has the PM compiled and issued the Terms of Reference and Professional Service Provider (PSP ) Guidelines to the Municipality Co-ordinator and/or NDP Panel (DBSA). | Compiled ToR and Guidelines and Email | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Has the MIS been updated with current project status | MIS updated | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
6 | Has the PM chaired the Briefing Session with the Consultant | Service Level Agreement Letter of Appointment Minutes Guidance Pack | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
7 | Has the Professional Service Provider (PSP) reviewed and updated the Work Plan including cash flow. | Updated the Work Plan including cash flow on file | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
8 | Has the PM, PD, CD and FD reviewed and approved the Work Plan including cash flow. | Updated the Work Plan including cash flow on file | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
9 | Has any changes to the Work Plan including cash flow been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH |  |  |  |  | YES | Accepted Urban Network Plans accepted against set criteria | YES | Total number of approved / revised Urban Networks |  | 3 | 3 | 0 | 0 | 0 | 1 | 1
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 27 | 24 | 0 | 0 | 0 | 1 | 1
[10 empty] | 0 | [10 empty] | 648

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0