## Process Flow
3 Precinct Planning
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 3.1 Conduct Precinct Design Planning | NDP – PP – 03 - 001 | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
Urban Network Phasing Plan
Toolkit
(Urban
Hub Design)
Professional Service Provider (PSP)
& Municipal Co-ordinator
Conduct Precinct & Sub Precinct Planning
3.1.1
1
Professional Service Provider (PSP)
& Municipal Co-ordinator
Conduct Precinct Studies
3.1.1
2
Precinct Status Quo Report
3.1.1(1)
MIS
Project Manager
Conduct a Compliance Check
3
O.K.
Yes
No
Project Manager
Raise a Change Request
4
Change
Request
Studies / Re-arrangement
Professional Service Provider (PSP)
& Municipal Co-ordinator
Develop Design Guidelines
3.1.2
6
Project Manager
Conduct a Informal Consultation
7
Minutes
MCO responsible to compile
Precinct Design
Framework
3.1.2(1)
Precinct Status QUO Report
3.1.1(1)
Design Guidelines
3.1.2(2)
Draft Precinct Design Plan
3.1.3(1)
Use as Input
Project Manager, Urban Planning Director, Chief Director+ Coordinator
Conduct a Technical Evaluation and Comment
3.1.4
8
Draft Precinct Design Plan
3.1.3(1)
File
As per file plan
Minutes
Professional Service Provider (PSP)
& Municipal Co-ordinator
Update Draft Precinct Design Plan as per the comments
9
Draft Precinct Design Plan (Updated)
3.1.3 (2)
Project Manager, Urban Planning Director
Conduct a Technical Evaluation and Comment
10
Draft Precinct Design Plan (Update)
O.K.
Yes
No
Project Manager
Raise a Change Request
11
Change
Request
Acceptance
Letter
Precinct Design Plan (Final)
3.1.3(2)
Chief Director
Sign Final Acceptance Letter
12
2.2 Urban Network Order Costing
MIS
MIS
MIS
Acceptance
Letter
3.1.4(1)
Precinct Design Plan (Final)
3.1.3(2)
3.2 Conduct Precinct Conceptual Planning
Checklist Required
Question
Acceptance must be done on MIS
Area For Improvement
Documentation can be uploaded and submitted via MIS
Note
Draft Precinct Design Plan must be issued to the task team at the same time. Task team includes the municipality
Area For Improvement
MUST INCLUDE SUB PRECINCT PHASING PLANS
1.1 Engage with Client
( Activity 14 )
Area For Improvement
Automatic notification of submitted documents
MIS
Area For Improvement
Automatic notification of submitted documents
Area For Improvement
Automatic notification of submitted documents
Area For Improvement
MIS to automatically generate the requested changes and send to the Municipal Co-ordinator / PSP (TA)
Area For Improvement
Can the Compliance Checklist used for the Precinct Status Quo Report be set as fields / tick boxes on the MIS
Area For Improvement
All received document to be automatically filed according to the agreed NDP File Plan
MIS
Area For Improvement
Automatic filling MIS
MIS
MIS
MIS
MIS
File
As per file plan
MIS
MIS
File
As per file plan
Checklist Required
MIS

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 3.1 Conduct Precinct Design Planning |  |  | 0% |  | 0 | 0 |  | 0 |  | 2 | 1 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recommendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | Has the PM conducted a compliance check of the "Precinct Status Quo Report" | "Precinct Status Quo Report" compliance check results and source of compliance check ( checklist ) | [8 empty] | HIGH |  |  |  |  | YES | Accepted "Precinct Status Quo Report" accepted against set criteria |  |  |  | 3 | 3 | 0 | 0 | 0 | 1 | 0
5 | Has any changes to the "Precinct Status Quo Report" been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
6 | Has a Technical Evaluation been conducted on the "Draft Precinct Design Plan" by the PM, PD and CD | Minutes of meeting with actions | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
7 | Has a Technical Evaluation been conducted on the "Updated Precinct Design Plan" by the PM and PD | "Updated Precinct Design Plan" comments and review available on file | [8 empty] | HIGH |  |  |  |  | YES | Accepted "Updated Precinct Design Plan" accepted against set criteria |  |  |  | 3 | 3 | 0 | 0 | 0 | 1 | 0
8 | Has any changes to the "Updated Precinct Design Plan" been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
9 | Has the PM issued a "Letter of Acceptance" to the PSP | "Letter of Acceptance" signed by the Chief Director and kept on file | [8 empty] | HIGH | [6 empty] | YES | Total number of approved Precinct Plans (Urban Hubs) |  | 3 | 3 | 0 | 0 | 0 | 0 | 1
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 27 | 26 | 0 | 0 | 0 | 2 | 1
[10 empty] | 0 | [10 empty] | 702

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0