## Process Flow
3 Precinct Planning
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 3.2 Conduct Precinct Conceptual Planning | NDP – PP – 03 - 002 | 0 | 2014-01-29
Municipal Interaction | ND INTERACTION |  |  | Municipal Interaction
Acceptance
3.3
Approval of table of NDP projects
3.1
Conduct Precinct Planning
Accepted
Precinct Design
Plan
PSP (TA) & Municipal Co-ordinator
Establish Precinct Phasing and Costing
3.2.1
1
Draft Precinct Phasing and Costing Plan
Project Manager, Planning Director & Chief Director
Conduct a Technical Evaluation and Comment
2
Draft Precinct Phasing , and Costing Plan
File
Project File
I-Drive
All Approved Documents in Legal File
Task Team
Evaluate Draft precinct Phasing and Costing Plan
and Comment
3
Minutes
Technical Advisor & Municipal Co-ordinator
Update Precinct Phasing and Costing Plan as per the comments
4
Precinct Phasing and Costing Plan (Update)
Project Manager, Planning Director
Conduct a Technical Evaluation
5
Precinct Phasing and Costing Plan (Update)
O.K.
Yes
No
Project Manager
Raise a Change Request
7
Change
Request
Acceptance
Letter
Precinct Phasing and Costing Plan (Update)
Chief Director
Sign Final Acceptance Letter
8
Outlook
Outlook
Acceptance
Letter
Precinct Phasing and Costing Plan (Accepted)
Outlook
Technical Advisor & Municipal Co-ordinator
Conduct a Feasibility Study and Prioritise
3.2.2
9
Precinct Design Plan (Final)
Precinct Design Plan (Final)
Precinct Design Plan (Final)
Draft Feasibility Study & prioritisation
Project Manager, Planning Director
Conduct a Technical Evaluation
10
Draft Feasibility Study & prioritisation
File
Project File
I-Drive
All Approved Documents in Legal File
Comments
Technical Advisor & Municipal Co-ordinator
Update Feasibility Study & prioritisation as per the comments
12
Feasibility Study & prioritisation (Updated)
Project Manager, Planning Director
Conduct a Technical Evaluation
13
Feasibility Study & prioritisation (Updated)
O.K.
Yes
No
Project Manager
Raise a Change Request
15
Change
Request
Acceptance
Letter
Feasibility Study & prioritisation (Updated)
Outlook
Outlook
Precinct Design Plan (Final)
Outlook
Precinct Phasing and Costing Plan
Area For Improvement
Acceptance could be done directly on MIS
Area For Improvement
This can be automated on MIS
Area For Improvement
Acceptance could be done directly on MIS
Area For Improvement
NEED A GUIDELINE ON WHAT Draft precinct Phasing , and Costing Plan
is
Area For Improvement
MUST INCLUDE SUB PRECINCT PHASING PLANS
Area For Improvement
ALL NDP AND OTHER PLANS NEED TO BE NOTED
Area For Improvement
GUIDLINES TO EVALUATE AGAINST MAY BE REQUIRED
Evaluation Checklist
Question
Should be approved on MIS
Checklist Required
Checklist Required
Question
Should this be approval / acceptance
Accepted
Precinct Design
Plan
Draft precinct Phasing , and Costing Plan
Task Team
Evaluate Draft precinct Phasing and Costing Plan
and Comment
3
Draft Feasibility Study & prioritisation
(Draft) Sub Precinct Concept Plans & Tabled of Prioritised Projects
COMPLETED PRECINCT PLAN
Project manager & Planning Director + Chief director
Evaluate Draft precinct Phasing and Costing Plan
and Comment
3
MIS
MIS
Area For Improvement
Automatic notification of submitted documents
3.1
Conduct Precinct Planning
Accepted
Precinct Design
Plan
Professional Service Provider (PSP)
& Municipal Co-ordinator
Establish Precinct Phasing and Costing
3.2.1
1
MIS
Draft Precinct Phasing and Costing Plan
MIS
Area For Improvement
NEED A GUIDELINE ON WHAT Draft precinct Phasing , and Costing Plan
is
Area For Improvement
MUST INCLUDE SUB PRECINCT PHASING PLANS
Area For Improvement
Automatic notification of submitted documents
Project Manager, Urban Planning Director & Chief Director
Conduct a Technical Evaluation and Comment
2
Draft Precinct Phasing , and Costing Plan
File
File Plan
Task Team
Evaluate Draft precinct Phasing and Costing Plan
and Comment
3
Precinct Design Plan (Final)
Precinct Design Plan (Final)
Evaluation Checklist
MIS
MIS
Minutes
Professional Service Provider (PSP)
& Municipal Co-ordinator
Update Precinct Phasing and Costing Plan as per the comments & minutes
4
MIS
Project Manager, Urban Planning Director
Conduct a Evaluation
5
Precinct Phasing and Costing Plan (Update)
MIS
Precinct Design Plan (Final)
MIS
O.K.
Yes
No
Project Manager
Raise a Change Request
6
Change
Request
MIS
Acceptance
Letter
MIS
Chief Director
Approve Final Acceptance Letter
7
Area for Improvement
Should be approved on MIS and MIS to automatically generate the Acceptance letter
Acceptance
Letter
MIS
Professional Service Provider (PSP)
& Municipal Co-ordinator
Conduct a Feasibility Study and prioritisation + Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects
3.2.2
8
Draft Feasibility Study & prioritisation
Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects
Project Manager, Urban Planning Director
Conduct a Technical Evaluation
9
Precinct Design Plan (Final)
MIS
Precinct Phasing and Costing Plan (Accepted)
MIS
Checklist Required
Comments
Professional Service Provider (PSP)
& Municipal Co-ordinator
Update Feasibility Study & prioritisation + Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects
as per the comments
10
MIS
Draft Feasibility Study & prioritisation
Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects
MIS
Project Manager, Urban Planning Director
Evaluate against comments issued
11
Area For Improvement
GUIDLINES TO EVALUATE AGAINST MAY BE REQUIRED
Checklist Required
MIS
Comments
O.K.
Yes
No
Project Manager
Raise a Change Request
12
Change
Request
MIS
Acceptance
Letter
MIS
Area for Improvement
Should be approved on MIS and MIS to automatically generate the Acceptance letter
Chief Director
Sign Final Acceptance Letter
13
Draft Feasibility Study & prioritisation (Accepted)
Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects (Accepted)
Precinct Phasing and Costing Plan (Accepted)
Acceptance
Letter
MIS
Professional Service Provider (PSP)
& Municipal Co-ordinator
COMPLETE FINAL PRECINCT CONCEPT PLAN
3.2.4
14
MIS
Feasibility Study & prioritisation (Accepted)
Sub Precinct Concept Plans & Tabled of Prioritised Projects (Accepted)
Precinct Phasing and Costing Plan (Accepted)
Accepted
Precinct Design
Plan
COMPLETED PRECINCT PLAN
3.3.
NDP PROJECTS IDENTIFICATION
MIS

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 3.2 Conduct Precinct Conceptual Planning |  |  | 0% |  | 0 | 0 |  | 0 |  | 2 | 2 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recommendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | Has a Technical Evaluation been conducted on the "Draft Precinct Phasing and Costing Plan" by the PM, PD and CD | Minutes of meeting with actions | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Has a Technical Evaluation been conducted on the "Updated Precinct Phasing and Costing Plan " by the PM and PD | "Updated Precinct Design Plan" comments and review available on file | [8 empty] | HIGH |  |  |  |  | YES | Accepted "Updated Precinct Phasing and Costing Plan " accepted against set criteria |  |  |  | 3 | 3 | 0 | 0 | 0 | 1 | 0
6 | Has any changes to the "Updated Precinct Phasing and Costing Plan " been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
7 | Has the PM issued a "Letter of Acceptance" to the PSP | "Letter of Acceptance" signed by the Chief Director and kept on file | [8 empty] | HIGH | [6 empty] | YES | Total number of approved Precinct Plans (Urban Hubs) |  | 3 | 3 | 0 | 0 | 0 | 0 | 1
8 | Has a Technical Evaluation been conducted on the "Draft Feasibility Study & prioritisation" and "Draft Sub Precinct Concept Plans & Tabled of Prioritised Projects" by the PM, PD and CD | Minutes of meeting with actions | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
9 | Has a Technical Evaluation been conducted on the Updated "Feasibility Study & prioritisation" and Updated "Sub Precinct Concept Plans & Tabled of Prioritised Projects" by the PM and PD | Updated "Draft Feasibility Study & prioritisation" and Updated "Sub Precinct Concept Plans & Tabled of Prioritised Projects"" comments and review available on file | [8 empty] | HIGH |  |  |  |  | YES | Accepted Updated "Feasibility Study & prioritisation" and "Sub Precinct Concept Plans & Tabled of Prioritised Projects" accepted against set criteria |  |  |  | 3 | 3 | 0 | 0 | 0 | 1 | 0
10 | Has any changes to the "Updated Precinct Phasing and Costing Plan " been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
11 | Has the PM issued a "Letter of Acceptance" to the PSP | "Letter of Acceptance" signed by the Chief Director and kept on file | [8 empty] | HIGH | [6 empty] | YES | Total number of approved Precinct Plans (Urban Hubs) |  | 3 | 3 | 0 | 0 | 0 | 0 | 1
12 | COMPLETE FINAL PRECINCT CONCEPT PLAN completed by the PSP | COMPLETE FINAL PRECINCT CONCEPT PLAN available on the MIS | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 36 | 35 | 0 | 0 | 0 | 2 | 2
[10 empty] | 0 | [10 empty] | 1260

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0