## Sheet1
Municipality (Oct) | Cashflow Progress |  | Project Description | PP Approved | PP Ceiling | Tender Value | Transfer | Web Spend | Remainder | Retention Approval | 2013/14 Gazette | Total Budget 13/14 | Planning | Adj Gazette | Cashflow Summaries | Ave Spend (6 mnths) | Spend July2014 | Planning | Design Development | Tender Stage | Implementation | Close Out | Comments
ANDILE S
CoCT | Due I Nov @ 10h00
Khayelitsha |  | 1 | EHO and Health Facility | Yes | 13900000 |  |  | 4040002 | 9859998 | [11 empty] | Yes | No
|  | 2 | Lentegeur Public Space and Civic Office | Yes | 10850000 |  |  | 29402400 | -18552400 | [11 empty] | Yes |  | Approval value vs Spend needs to be resolved.
|  | 3 | Lentegeur/Mandalay Transport Interchange | Yes | 11000000 |  |  | 34313550 | -23313550 | [13 empty] | Approval value vs Spend needs to be resolved.
[5 empty] | 24750000 |  |  | 33442402 | -32005952 | 16436000 | 30000000 | 46436000 |  | 30000000 | 46436000 | [7 empty] | Funds transferred but need cashflows for monitoring
NMBM | Submitted
Njoli Square |  |  |  |  | 121000000 |  |  | 6970449 | 114029551 | [5 empty] | 10000000
Fountain Rd |  | 4 | Youth Development Centre | Yes | 29213765 |  |  | 15454678 | 13759087 | [5 empty] | 5208807 |  |  |  | Yes |  |  | No
|  | 5 | Advice Centre | Yes | 19905499 |  |  | 8370354 | 11535145 | [5 empty] | 1548607 |  |  |  | Yes
[5 empty] | 49119264 |  |  | 23825032 | 25294232
Helenvale |  | 6 | Kobus Rd Renewal Phase 2 | Yes | 7638000 | [9 empty] | 7200000 | [6 empty] | No | Should not reflect - spend of R3+ and savings
7638000
Motherwell |  | 7 | SMME Hive | Yes | 9150000 |  |  | 0 | 9150000 | [5 empty] | 9150000 |  |  |  | Yes |  |  | No | Check
[5 empty] | 9150000 |  |  |  |  | 0 | 70000000 | 70000000 |  | 39267414 | 39267414 | 2275140 | 15925981
City of Matlosana | No approved PPs | [8 empty] | 0 | 10000000 | 10000000
[11 empty] | 10000000 | 10000000 |  |  | 0
SIFISHO H
Newcastle | Submitted | 8 | Madadeni Transport Node | ? | 14178000 |  |  | 785000 | 13393000 | [12 empty] | No
|  | 9 | Osizweni Taxi rank | ? | 8925000 |  |  | 1962000 | 6963000 | [12 empty] | No
|  | 10 | MAD 4 Road | ? | 21322000 |  |  | 19679000 | 1643000 | [12 empty] | No | Approval value vs Spend needs to be resolved.
[5 empty] | 44425000 |  |  | 22426000 | 21999000 |  | 9529000 | 9529000 |  | 3500000 | 24114000 | 388586 | 2720103 | [5 empty] | Assump is R500,000 spend pm
Polokwane | No approved PPs | [9 empty] | 5000000 | 5000000
[11 empty] | 5000000 | 5000000 |  |  | 0
LITEBOHO M
CoJ | Submitted | 11 | Ngonyama Activity Street Phase 2 | Yes | 26000000 |  | 30232569 | 13438060 | 12561940 |  | 20000000 | [11 empty] | Web report PP ceiling differs
|  | 12 | Alex -Marlboro Auto Industrial Cluster | Yes | 0 |  |  | 0 | 0 |  | 0 | [11 empty] | Pipeline Project
|  | 13 | Bambanani Auto Industrial Cluster | Yes | 0 |  |  | 0 | 0 |  | 0 | [11 empty] | Pipeline Project
[5 empty] | 26000000 |  |  | 13438060 | 12561940 | 0 | 20000000 | 60000000 |  | 32868000 | 32868000
CoT | Submitted | 12 | Upgrading of Public Infrastructure -Mamelodi | Yes | 15163600 |  |  | 13059042 | 2104558 |  | 5395921
|  | 13 | Solomon Mahlangu Freedom Square Redevelopment | Yes | 15000000 |  |  | 4284659 | 10715341 |  | 12500000 |  |  |  | 9784224
|  | 14 | Urban Agriculture | Yes | 6000000 |  |  | 0 | 6000000 |  | 6000000
|  | 15 | Saulsville Footbridge Precinct | Yes | 9690000 |  |  | 243092 | 9446908 |  | 6558468 |  |  |  | 8974561
|  | 16 | Soshanguve/Mabopane Taxi & Bus Ranks | Yes | 39104700 |  |  | 2761079 | 36343621 |  | 34604700 |  |  |  | 26035000
|  | 17 | Mabopane Walkways | Yes | 38339397 |  |  | 36951313 | 1388084 |  | 7450965 |  |  |  | 17081927 | over
|  | 18 | Hammanskraal CBD Walkways and NMT | Yes | 12399616 |  |  | 11760520 | 639096 |  | 416356
|  | 19 | Temba Pedestrian Walkways and NMT | Yes | 23938903 |  |  | 23803750 | 135153 |  | 2235011
|  | 20 | Pedestrian Bridge across Route R101 | Yes | 42935380 |  |  | 2353547 | 40581833 |  | 42935380 |  |  |  | 35297342
|  | 21 | Link Road from Church Street to Atteridgeville | Yes | 3682884 |  |  | 0 | 3682884 |  | 3682884 |  |  |  | 3498740
|  | 22 | Pedestrianisation of road netwroks & intersection upgrade | Yes | 46410613 |  |  | 2510372 | 43900241 |  | 2435315 |  |  |  | 38896628
[5 empty] | 252665093 |  |  | 97727374 | 154937719 | 2360000 | 124215000 | 126575000 |  | 210429263 | 210429263
Mogale City | Due on 25th Oct | 23 | Pedestrian Walkways and Public Environment Upgrade | Yes | 10000000 | [5 empty] | 10000000 | 10000000
[5 empty] | 10000000 | [5 empty] | 10000000 | 10000000 |  | 10000000 | 10000000
Ekurhuleni | No approved PPs | [9 empty] | 10000000 | 10000000
[11 empty] | 10000000 | 10000000 |  | 10000000 | 10000000
EUGENIE N
Ethekwini | Already spent - | 24 | Western Station | ? | 60000000 |  |  | 5228000 | 54772000 |  |  |  | Status? | [7 empty] | Check Status | Yes
| updated web report |  |  |  | 60000000 |  |  | 5228000 | 54772000 |  | 3555000 | 3555000 |  | 3555000 | 3555000 | 0 | 0
requested
SIFISO M
Mogalakwena | Submitted | 25 | Mahwelereng Corridor Upgrade | Yes | 63442000 |  |  | 31804000 | 31638000 | [11 empty] | Yes
[5 empty] | 63442000 |  |  | 31804000 | 31638000 | 6913000 | 32941000 | 39854000 |  | 27368330 | 27368330 | 3400000 | 23800000
Sedibeng | Submitted | 26 | Sebokeng Cultural Precinct | Yes | 18205000 |  |  | 635000 | 17570000 | [11 empty] | Yes
[5 empty] | 18205000 |  |  | 635000 | 17570000 |  | 16205000 | 16205000 |  | 5000000 | 16205000 | 634723 | 4443061
Matzikama | Not required | 27 | Transport Interchange | ? | 452000 |  |  | 0 | 452000 | [12 empty] | Check Status
|  | 28 | Creche and taxi shelter | ? | 400000 |  |  | 800000 | -400000 | [11 empty] | Yes | Required | Over Expenditure
|  | 29 | Pedestrian Routes | ? | 2712000 |  |  | 2385000 | 327000 | [11 empty] | Yes | Check Status
|  | 30 | Greening | ? | 2825000 |  |  | 4090000 | -1265000 | [11 empty] | Yes | Required | Over Expenditure
[5 empty] | 6389000 |  |  | 7275000 | -886000 |  | 2800000 | 2800000 |  | 2800000 | 0 | 621123 | 4347860 | [5 empty] | SP cashflows not required
Senqu |  | 31 | Sterkspruit Settlement Planning/Upgrade |  | 7310250 |  |  | 5713979 | 1596271 | [12 empty] | Appears to be closed | Transfer amount exceeds approved value
[5 empty] | 7310250 |  |  | 5713979 | 1596271 | 1348000 | 1287000 | 2635000 |  | 0 | 0 | 0 | [5 empty] | Required | 50% web reporting
Ndwedwe | Submitted | 32 | Road Signage | ? | 1228709 |  |  | 849893 | 378816 | [11 empty] | Yes
[5 empty] | 1228709 |  |  | 849893 | 378816 |  | 19768000 | 19768000 |  | 3500000 | 34030610 | 500000 | 3500000 | [5 empty] | Proposed R500,000 pm
Nongoma | Submitted | 33 | Bus and Taxi Ranks | ? | 38207000 |  |  | 26995591 | 11211409 | [11 empty] | Yes
|  | 34 | Main Rd Rehab | ? | 37146000 |  |  | 12490209 | 24655791 | [11 empty] | Yes
[5 empty] | 75353000 |  |  | 39485800 | 35867200 |  | 26100000 | 26100000 |  | 30000000 | 42000000 | 4325273 | 30276911
Umzimkhulu | Submitted | 35 | Road 2131 | ? | 11602000 |  |  | 6255784 | 5346216 | [11 empty] | Yes
|  | 36 | Road 2129 |  | 13971000 |  |  | 7492246 | 6478754 | [11 empty] | Yes
[5 empty] | 25573000 |  |  | 13748030 | 11824970 | 2068000 | 21000000 | 23068000 |  | 10000000 | 13799226 | 1564771 | 10953399
Amathole | Not required | 37 | Stutterheim Community Commercial Park | Yes | 49193740 |  |  | 47631849 | 1561891 | [11 empty] | Check Status |  | Check Close out report status
|  | 38 | Hamburg Regeneration | Yes | 14401807 |  |  | 10020096 | 4381711
[5 empty] | 63595547 |  |  | 57651945 | 5943602 |  | 0 | 0 |  | 0 | 0 | [7 empty] | SP cashflows not required
Greater Tzaneen | Submitted | 39 | Broadband | Yes | 5332000 |  |  | 4070000 | 1262000 | [12 empty] | 2014-02-01 | Maintenance contract running -12 months
|  | 40 | Community Park | Yes | 5332000 |  |  | 4134000 | 1198000 | [11 empty] | ? | 2014-07-01
|  | 41 | Nkowankowa CBD Redevelopment | Yes | 23099000 |  |  | 647000 | 22452000 | [11 empty] | ? | 2014-10-01 | Waiting for municipal approval .
|  | 42 | Nkowankowa East | Yes | 30935444 |  |  | 10012680 | 20922764 | [11 empty] | Yes | 2014-07-01
|  | 43 | Ritavi Rehabilitation | Yes | 5449000 |  |  | 4721000 | 728000 | [12 empty] | 2014-07-01
[5 empty] | 64815444 |  |  | 19514680 | 45300764 | 3350000 | 30347000 | 33697000 |  | 15000000 | 28442000 | 1156326 | 8094280
Ramotshere Moiloa | Submitted | 44 | MPCC | Yes | 26484000 |  |  | 13115332 | 13368668 | [11 empty] | Yes
[5 empty] | 26484000 |  |  | 13115332 | 13368668 | 2780000 | 13000000 | 15780000 |  | 6000000 | 15279707 | 497687 | 3483809
Thulamela | Submitted | 45 | Thoyoyandou | Yes | 124321071 |  |  | 104422681 | 19898390 | [11 empty] | Yes
|  | 46 | Sibasa | Yes | 24508000 |  |  | 7601000 | 16907000 | [11 empty] | Check Status
|  | 47 | Malamulele | Yes - budget limit | 37080000 |  |  | 14336704 | 22743296 | [11 empty] | Check Status
[5 empty] | 185909071 |  |  | 126360385 | 59548686 |  | 16000000 | 16000000 |  | 27000000 | 65516020 | 3000000 | 21000000
Emnambithi /Ladysmith | Submitted | 48 | Trading Stalls | ? | 2095000 |  |  | 1702000 | 393000
|  | 49 | Link Road | Yes | 24500000 |  |  | 10260531 | 14239469
|  | 50 | Bridge | ? | 15494000 |  |  | 17182000 | -1688000
[5 empty] | 42089000 |  |  | 29144531 | 12944469 | 157000 | 1937000 | 2094000 |  | 20000000 | 28513770 | 2747161 | 19230128
KwaDukuza | Submitted | 51 | Woodmead Transport Node | ? | 37072000 |  |  | 5054702 | 32017298 | [11 empty] | Yes
|  | 52 | Woodmead Intersection Upgrade /Access Rd | ? | 7442889 |  |  | 1514191 | 5928698 | [11 empty] | Yes
[5 empty] | 44514889 |  |  | 6568893 | 37945996 |  | 23000000 | 23000000 |  | 4243000 | 38074637 | 565593 | 3959153
Makana | Not required | 53 | Memorial Node | ? | 26170000 |  |  | 6873062 | 19296938
|  | 54 | Node 2 Development | ? | 33720000 |  |  | 32691000 | 1029000
[5 empty] | 59890000 |  |  | 39564062 | 20325938 |  | 20491000 | 20491000 |  | 5841000 | 0 | 1795527 | 12568689 | [5 empty] | SP cashflows not required
Metsweding | Not required | 55 | Refilwe Development Business Node | ? | 11447000 |  |  | 2692000 | 8755000 | [11 empty] | Yes
[5 empty] | 11447000 |  |  | 2692000 | 8755000 |  |  |  |  | 0
Steve Tshwete | Submitted | 56 | Community Civic Node | Yes | 29626331 |  |  | 20151315 | 9475016 | [11 empty] | Yes
[5 empty] | 29626331 |  |  | 20151315 | 9475016 | 3149000 | 5000000 | 8149000 |  | 8393135 | 8393135 | 1462963 | 10240739
Greater Taung | Submitted | 57 | CBD Regeneration | Yes | 59430547 |  |  | 44382111 | 15048436 | [11 empty] | Yes
[5 empty] | 59430547 |  |  | 44382111 | 15048436 |  | 20466000 | 20466000 |  | 30000000 | 30000000 | 1242601 | 8698207
Beaufort West | Not required | 58 | Pedestrian Walkways and Roads | ? | 2034240 |  |  | 5107572 | -3073332
[5 empty] | 2034240 |  |  | 5107572 | -3073332 |  |  |  |  | 0 | 0
Mandeni | Not required | 59 | Mandeni CBD Upgrade | Yes | 30000000 |  |  | 1259246 | 28740754
[5 empty] | 30000000 |  |  | 1259246 | 28740754 |  |  |  |  | 0 | 0
Umtshezi | Not required | 60 | Taxi Rank |  | 6721873 |  |  | 4733763 | 1988110
|  | 61 | Multi Purpose Sports Centre |  | 3000000 |  |  | 3662179 | -662179
[5 empty] | 9721873 | [8 empty] | 0 | 0
1310806258
[9 empty] | 195145465 |  | 542641000 | 611202000 |  | 534765142 | 704292112 |  | 183242320
| KEY: |  | Yellow indicated close outs that can be anticipated by end of muni financial year. | [10 empty] | 598000000
63234858
PIPELINE PROJECTS | [8 empty] | Add R87,000,000 for pipeline
CoJ | Required ? | 1 | Alex -Marlboro Auto Industrial Cluster | Yes | 21000000 |  |  | 0 | 21000000 |  | 10009813 |  |  |  | 18000000
| Required ? | 2 | Bambanani Auto Industrial Cluster | Yes | 32000000 |  |  | 0 | 32000000 |  | 6908948 |  |  |  | 26500000
CoT | Required ? | 3 | Atteridgeville Predestrianisation and Intersection Upgrade | No | 46411000
| Required ? | 4 | Atteridgeville Church Str /Atteridgeville Station Link | No | 3683000 | [11 empty] | 87000000
| Required ? | 5 | Hammanskraal Predestrian Bridge | No | 42935000 | [11 empty] | 23765142
| Required ? | 6 | Atteridgeville Informal Traders Stalls | No | 13593000
| Required ? | 7 | Hammanskraal Circular Road Network | No | 11715000
| Required ? | 8 | Hammanskraal Road Link from Renbro Centre | No | 5437000
176774000
87000000
23765142
|  | 9 | Atteridgeville Pedestrianisation of Seiso | No
|  | 10 | Hammanskraal West Linkage Road | No
|  | 11 | Solomon Mahlangu Freedom Square Phase 2 | No
|  | 12 | Tsamaya Activity Spine Phase 1 | No
|  | 13 | Tsamaya Activity Spine Phase 2 | No
City of Matlosana |  | 14 | Jouberton Pedestrian Bridge | No | 21625000 | [9 empty] | 21625000 | 21625000
Polokwane
Ekurhuleni
Msunduzi |  |  |  |  | 20350000 | [9 empty] | 20350000 | 10175000
I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\New Approach Shared Folder\CG Status Quo_Oct 2013 | [14 empty] | 41975000 | 31800000
Note on T111: Lee Rosenzweig: