## Sheet1
Draft A.02 dated 2014 05 27
See note in cell G2
| CD | FIN | PPM Committee | PPM (Planning) | Planning | Implementation
See note in cell G12
When does PPM take over to run the PPM process
Prioritisation must be dicussed
Remove Committee Meeting
| CD | FIN | PPM Committee | PPM | TA | CG
Reasons for committee (if necessary)
| CD | FIN | PPM Committee | PPM | TA | CG
Note on G2: Johan Coetzee: Project PPM is defined as (i) S.Pennypacker as project identification, generation of data, evaluation, selection and prioritisation (ii) by PMI Portfolio (Pf) Management Strategic Management, Pf Governance Management, Pf Perfomance Management, Pf Communication Managment & Pf Risk Management
Note on G12: Johan Coetzee: Depending on the informationa available on the project, the Cost of Works can be a subjective estimate without any information on the product breakdown structure or an etstimate from the Municipality/Consultants or if the Product breakdown is available, but without a cost estimate, the CG Benchmarking tool can be used. No cash flows availble at this stage, only the basic project information as per Project Info Sheet with available supporting innformation to substantiate the cost estimate
Read annual budget from MIS (min 10 years)
From TA - (i) List of Prioritised Projects OR (ii) addition of 1 or few projects
From TA Process 3.3
Pre-screening and ACCEPTANCE of prioritised "stack" of projects ready for portfolio analysis
Notification of projects NOT accepted during pre-screening
Project Portfolio scenario analyses
FIN
annual budgets inputs
Established preferred schedule of projects with portfolio cash flow requirement
PPM Committee review and ACCEPT preferred schedule of projects and measured against CG annual budget
Not accepted - update PPA
Prepare final planned project cash flow and start and end dates per stage for the project and final portfolio cash flow requirement measured against available budget
Document 1- PPA printouts showing total portfolio cash flow requirement against available budget and cash flow printout of projects that make up the total cash flow requirement and submits to FIN to obtain portfolio bottom line budget approval - it includes annual budget for 1 + 3 years and cumulative allocated funds to for 1 + 3 years
FIN review total portfolio annual requirements and ACCEPTS total portfolio cash flow requirement
Not accepted - update PPA
PPM arrange PPM Committee Review Meeting
Accepted portfolio cash flow requirement
Complete Project Baseline 0 Template (which must show if full or partial project is funded) for each project including required cash flows per months, enter cash flow requirements into MIS
Once cash flow is entered into MIS then compile Project "to Proceed" Document consisting of
(i) Baseline 0 document
(ii) Copy of MIS cash flow printout and checked against Baseline and (optional) the original Project Info sheet
Present possible scenarios and accepted preferred schedule of projects, the related portfolio cash flow requirement measured against available budget
APPROVE to proceed with Implementation process i,e,
(i) Existing projects
(ii) New projects
(a) full project to be funded
(b) Partial project to be funded
(iii) Projects to remain in pipeline and not be be funded yet
Project Implementation Director receives notification "to proceed with project" and "allocated funds" to the full project of part of the project = Start of Implementation Process "Gate to Proceed"
START OF PPM PROCESS
END OF PPM PROCESS
Accepted preferred portfolio schedule
FIN formally approves (Document 1) portfolio cash flow requirement measured against budget
Approved total portfolio cash flow requirement
prepare Document 2- PPA printouts showing each project's cash flow requirement per stage and per project
Approved projects to proceed with full of partial funding requirements
Projects not approved
FIN to "allocate" and "release" funds as per baseline document /MIS
PPM freeze portfolio information and notify (per MIS or other method) Project Implementation Director to proceed (approvals available)
Establish Implementation prioritisation
Complete New Project Info Sheets OR Update Existing Project Info Sheets: Prioritised "stack" of Project Info sheets