## Process Flow
5 Implementation
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 5.2 Concept Viability - Stage 2 (Preliminary Design) | NDP – IM – 03 - 002 | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
5.1 Inception - Stage 1
Preliminary Project Execution Plan
Municipal Co-ordinator and Professional Service Provider (PSP)
Undertake Preliminary Design
1
Project Concept
Project Manager
Complete the Benchmarking tool
2
Project Concept Baseline
Project Manager & Project Implementation Director
Review against the Preliminary Project Execution Plan
3
Preliminary Project Execution Plan
O.K.
Yes
No
Project Manager
Raise a Change request
4
Change Request
MIS
Project Concept Baseline
Project Manager
Capture into MIS
5
MIS
Project Concept Baseline
Project Concept Baseline
File
I Drive File
5.3
Design Development - Stage 3
(Detail Design)
Includes :
- Preliminary Bill of Quantities
- Investigations
- Study Reports
- Preliminary Design
- Baseline Costing
- Cash Flow
Area For Improvement
BENCHMARKING TOOL OUTPUT MUST BE UPLOADED INTO MIS
Area For Improvement
Aesthetics requirements must be included
Budget Input CG
Project Concept Baseline Cashflow
Area For Improvement
Update project portfolio on MIS.
Will it be possible for MIS to automaticaly update the project portfolio on the upload of the project concept baseline.
Project Manager
Update the project portfolio on MIS
(This is a risk as the cashflow must be approved before uploading)
6
MIS
Area For Improvement
Business rules on the on cashflow variances must be buit into MIS. Variances must be approved prior to cashflow update
MIS
MIS
MIS
MIS
MIS

## High Level Table
PROGRAMME MANAGEMENT (HIGH-LEVEL PROCESS AND BENEFITS REALISATION)
Management Approach: Urban Network and Precinct Development (Phases, Milestones, Gates, Baselines, Deliverables, Reviews, Audits)
PHASE | 1 Programme Initiation |  |  |  |  | 2 Network Planning |  | 3 Precinct Planning |  |  | 4 Implementation
| 1A | 1B | 1C | 1D | 1E | 2A | 2B | 3A | 3B | 3C | 4A | 4B | 4C | 4D | 4E | 4F
| 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 2.1 | 2.2 | 3.1 | 3.2 | 3.3 | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6
SUBPHASE | Engage with the Client | Establish Work Plan | Identify Urban Network Elements | Conclude Contrcatual Arrangements | Appoint TA Consultant(s) , final Work Plan and Funds | Conduct Urban Network Phasing | UN Order Costing | Conduct Precinct Planning | Conduct Precinct Concept Planning | Listing and Prioritising of NDP Projects | Inception Stage | Feasibility / Preliminary Design ( Concept & Viability ) | Detail Design ( Design Development ) | Tender ( Documentation and Procurement ) | Construction ( Contract Administration and Inspection ) | Close-out
MILESTONE |  |  | 1 | 2 |  |  | 3 | 4 | 5 | 6 |  |  | 7 | 8 | 9 | 10
GATES | 1.3: 1; 1.4: 2; 2.2: 3; 3.1: 4; 3.2: 5; 3.3: 6; 4.3: 7; 4.4: 8
BASELINES | 2.2: Urban Network Baseline; 3.2: Precinct Baseline; 4.2: Project Concept Baseline 1; 4.3: Project Tender Baseline 2; 4.4: Project Construction Baseline 3
DELIVERABLES | Minutes of Engagement meetings | Work Plan | UN ID map | Council Submission | Terms of Reference | Urban Network Planning Plan | Updated Network Phasing Plan ( including High Order Costing ) | Precinct Design Plan | Precinct Phasing Plan and Precinct Concept Plan ( Spatial, High Level SDP and Phasing ) | Table of Prioritised Projects ( name, Scope, End Dates, Costing ) | Confirmation of Precinct Scope requirement. | Feasibility Study Reports | Tender Drawings, Documents and Costing from BoA | Contract Award | Delivered Construction Project with AS BUILT Drawings | Close-out Reports
| Institutional arrangement |  | Map description table | Council Resolution | Letter of Appointment |  | NDP Letter of Acceptance | NDP Letter of Acceptance |  |  | Project Execution Plan | Preliminary Design Drawings |  | Final Construction Phase Estimate
|  |  | Letter of NO Objection | MOA for NDP grant | SLA | [5 empty] | Agreement
Consultant Guidance Pack
Updated Work Plan
Approval / Acceptance by NDP | 1.2: Acceptance; 1.3: Letter of NO Objection; 1.4: Signing of MOA for NDP Grant; 1.5: Approval of Updated Work Plan; 2.2: NDP Letter of Acceptance; 3.1: NDP Letter of Acceptance; 3.2: NDP Approval Letter
REVIEWS | 3.2: Precinct Concept Review; 4.2: Preliminary Design review; 4.3: Critical Design Review
AUDITS | 3.1: From 1.3; 3.2: From 2.1; 3.3: From 3.2; 4.3: Functional; 4.5: Physical

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 4.2 Concept Viability - Stage 2 (Preliminary Design) |  |  | 0% |  | 0 | 0 |  | 0 |  | 1 | 1 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recomendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | Has the PM completed the Project Benchmarking Tool using the Project Concept submitted by the PSP | Completed Project Benchmarling Tool ( Project Concept Baseline ) | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
5 | Is there minutes of the Technical Evaluation of the Preliminary Project Execution Plan by the PM and ID | Minutes | [8 empty] | HIGH |  |  |  |  | YES | Accepted "Project Concept Baseline" accepted against set criteria | YES | No of approved projects in implementation (as % of gazette) |  | 3 | 3 | 0 | 0 | 0 | 1 | 1
6 | Has any changes to the "Project Concept Baseline " been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 18 | 16 | 0 | 0 | 0 | 1 | 1
[10 empty] | 0 | [10 empty] | 288

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0