National Treasury

Corporate Services

Chief Directorate: Neighbourhood Development Program

Core Business Operational Procedures

| Document No | NDP- |
| --- | --- |
| Version No |  |
| Owner | David Van Niekerk |
| Release Date |  |
| Document Classification |  |
| Compiled by | D.J.Korff |

Glossary of Abbreviations

| Abbreviation | Description |
| --- | --- |
| BP | Business Plan |
| CD | Chief Director |
| IGR | Intergovernmental Relations |
| MIS | Management Information System |
| NDP | Neigborhood Development Programme |
| NT | National Treasury |
| PA | Project Administrator |
| PM | Project manager |
| PP | Project Plan |
| PD | Project Director |
| PDF | Portable Document Format |
| SLA | Service level Agreement |
| TOR | Terms of reference |
| TA | Technical Assistance |

Document Reference Library

| Document File Name | Context and Relevance |
| --- | --- |
| NDP Strategic Business Plan | Provide direction on future processes |
| NDP Annual Performance Plan | Provide direction on future processes |
| NDP Standard Operating Procedures | Provide information on existing processes |
| DOR Act | Provide compliance requirements |
| Neighborhood Development Partnership Grant | Provide compliance requirements |
| Applicable legislation / regulations | Provide compliance requirements |

Amendment History

| Version | Release Date | Description of Amendment | Amended By |
| --- | --- | --- | --- |
| 0 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

TABLE OF CONTENTS

Introduction	6

Purpose	6

Document Scope	6

Business Process Decomposition	7

Identified Roles	9

Procedures	10

Procedure Name: Advertise the Grant	10

Procedure Name: Assess Municipal Applications	14

Procedure Name: Formalise the Funding Agreement	18

Procedure Name: Review Operational Guide for Municipalities	22

Procedure Name: Induct Municipal Officials	26

Procedure Name: Validate Service Provider	30

Procedure Name: Scope Programme	34

Procedure Name: Develop Programme Business Case	37

Procedure Name: Assess Portfolio	41

Procedure Name: Allocate Award	44

Procedure Name: Formalise the Funding Agreement	47

Procedure Name: Review Operational Guide for Municipalities	50

Procedure Name: Induct Municipal Officials	54

Procedure Name: Validate Service Provider	58

Procedure Name: Scope Programme	62

Procedure Name: Develop Programme Business Case	65

Procedure Name: Manage Precincts	68

Procedure Name: Review / Approve Project Plans	71

Procedure Name: Close Out Project	77

Procedure Name: Review BP / Programme	81

Procedure Name: Monthly Reporting	85

Procedure Name: Re-align Project Work Plans	89

Procedure Name: Segment Municipalities	93

Procedure Name: Municipal Performance Protocol	96

Procedure Name: Prioritise Pipelined Projects	99

Procedure Name: MTEF Budget	102

Procedure Name: In Year Budget	106

Procedure Name: DORA Payment Schedule	110

Procedure Name: TA Invoice Payment	114

Procedure Name: CG Draw Down	118

Procedure Name: Retain Unspent Municipal Funds	122

Procedure Name: Submit Section 10 Reports	126

Procedure Name: Generate Innovation Products	130

Procedure Name: Mainstream Innovation Products	134

Authorisation	137

TABLE OF FIGURES

Figure 1: NDP Business Processes (To Be)	7

Figure 2: Procedure Scopes	8

Figure 3: Example Diagram	9

Figure 4: NDP Core Business Roles	9

Figure 5: Procedure Scope: Advertise the Grant	10

Figure 6: Procedure Model: Advertise the Grant	11

Figure 7: Procedure Scope: Assess Municipal Applications	14

Figure 8: Procedure Model: Assess Municipal Applications	15

Figure 9: Procedure Scope: Formalise the Funding Agreement	18

Figure 10: Procedure Model: Formalise the Funding Agreement	19

Figure 11: Procedure Scope: Review Operational Guide for Municipalities	22

Figure 12: Procedure Model: Review Operational Guide for Municipalities	23

Figure 13: Procedure Scope: Induct Municipal Officials	26

Figure 14: Procedure Model: Induct Municipal Officials	27

Figure 15: Procedure Scope: Validate Service Provider	30

Figure 16: Procedure Scope: Scope Programme	34

Figure 17: Procedure Model: Scope Programme	35

Figure 18: Procedure Scope: Develop Programme Business Case	37

Figure 19: Procedure Model: Develop Programme Business Case	38

Figure 20: Procedure Scope: Assess Portfolio	41

Figure 21: Procedure Model: Assess Portfolio	42

Figure 22: Procedure Scope: Allocate Award	44

Figure 23: Procedure Model: Allocate Award	45

Figure 24: Procedure Scope: Formalise the Funding Agreement	47

Figure 25: Procedure Model: Formalise the Funding Agreement	48

Figure 26: Procedure Scope: Review Operational Guide for Municipalities	50

Figure 27: Procedure Model: Review Operational Guide for Municipalities	51

Figure 28: Procedure Scope: Induct Municipal Officials	54

Figure 29: Procedure Model: Induct Municipal Officials	55

Figure 30: Procedure Scope: Validate Service Provider	58

Figure 31: Procedure Model: Validate Service Provider	59

Figure 32: Procedure Scope: Scope Programme	62

Figure 33: Procedure Model: Scope Programme	63

Figure 34: Procedure Scope: Develop Programme Business Case	65

Figure 35: Procedure Model: Develop Programme Business Case	66

Figure 36: Procedure Scope: Manage Precincts	68

Figure 37: Procedure Model: Manage Precincts	69

Figure 38: Procedure Scope: Review / Approve Project Plans	71

Figure 39: Procedure Model: Review / Approve Project Plans	72

Figure 40: Procedure Scope: Close Out Project	77

Figure 41: Procedure Model: Close Out Project	78

Figure 42: Procedure Scope: Review BP / Programme	81

Figure 43: Procedure Model: Review BP / Programme	82

Figure 44: Procedure Scope: Monthly Reporting	85

Figure 45: Procedure Model: Monthly Reporting	86

Figure 46: Procedure Scope: Re-align Project Work Plans	89

Figure 47: Procedure Model: Re-align Project Work Plans	90

Figure 48: Procedure Scope: Segment Municipalities	93

Figure 49: Procedure Model: Segment Municipalities	94

Figure 50: Procedure Scope: Municipal Performance Protocol	96

Figure 51: Procedure Model: Municipal Performance Protocol	97

Figure 52: Procedure Scope: Prioritise Pipelined Projects	99

Figure 53: Procedure Model: Prioritise Pipelined Projects	100

Figure 54: Procedure Scope: MTEF Budget	102

Figure 55: Procedure Model: MTEF Budget	103

Figure 56: Procedure Scope: In Year Budget	106

Figure 57: Procedure Model: In Year Budget	107

Figure 58: Procedure Scope: DORA Payment Schedule	110

Figure 59: Procedure Model: DORA Payment Schedule	111

Figure 60: Procedure Scope: TA Invoice Payment	114

Figure 61: Procedure Model: TA Invoice Payment	115

Figure 62: Procedure Scope: CG Draw Down	118

Figure 63: Procedure Model: CG Draw Down	119

Figure 64: Procedure Scope: Retain Unspent Municipal Funds	122

Figure 65: Procedure Model: Retain Unspent Municipal Funds	123

Figure 66: Procedure Scope: Submit Section 10 Reports	126

Figure 67: Procedure Model: Submit Section 10 Reports	127

Figure 68: Procedure Scope: Generate Innovation Products	130

Figure 69: Procedure Model: Generate Innovation Products	131

Figure 70: Procedure Scope: Mainstream Innovation Products	134

Figure 71: Procedure Model: Mainstream Innovation Products	135

- TABLE OF TABLES

Table 1: Advertise the Grant	12

Table 2: Assess Municipal Applications	16

Table 3: Formalise the Funding Agreement	20

Table 4: Review Operational Guide for Municipalities	24

Table 5: Induct Municipal Officials	28

Table 6: Validate Service Provider	32

Table 7: Scope Programme	36

Table 8: Develop Programme Business Case	39

Table 9: Assess Portfolio	43

Table 10: Allocate Award	46

Table 11: Formalise the Funding Agreement	49

Table 12: Formalise the Funding Agreement	52

Table 13: Induct Municipal Officials	56

Table 14: Validate Service Provider	60

Table 15: Scope Programme	64

Table 16: Develop Programme Business Case	67

Table 17: Manage Precincts	70

Table 18: Review / Approve Project Plans	73

Table 19: Close Out Project	79

Table 20: Review BP / Programme	83

Table 21: Monthly Reporting	87

Table 22: Re-align Project Work Plans	91

Table 23: Segment Municipalities	95

Table 24: Municipal Performance Protocol	98

Table 25: Prioritise Pipelined Projects	101

Table 26: MTEF Budget	104

Table 27: In Year Budget	108

Table 28: DORA Payment Schedule	112

Table 29: TA Invoice Payment	116

Table 30: CG Draw Down	120

Table 31: Retain Unspent Municipal Funds	124

Table 32: Submit Section 10 Reports	128

Table 33: Generate Innovation Products	132

Table 34: Mainstream Innovation Products	136

# Introduction

- Operational procedures were identified during the development/review of the National Treasury PROCESS NAME Business Architecture. The operational procedures describe specific operational activities. The procedures serve several, if not all, of the following purposes:

  - It prescribes the events triggering the execution of the procedure.

  - It prescribes specific activities to be executed.

  - It prescribes specific responsibilities (specific roles related to specific activities).

  - It prescribes specific business rules guiding decision-making within the procedure.

  - It prescribes information flow between activities.

  - It prescribes which information items should be managed as quality records.

  - It prescribes the use of specific technology systems.

  - It prescribes the event ending the execution of the procedure.

## Purpose

- The aim of this document is to serve as formal record of documented operational procedures supporting the PROCESS NAME Business Architecture.

## Document Scope

- After the introductory part the document starts with a model representing an overview of NDP business processes and procedures. Each of the procedures that follows are described in the following order:

  - The first model creates a scope for the procedure followed by a model representing a flow of activities, information and responsibilities.

  - This process flow is followed by a more detailed description of the elements which form part of the procedure.

- Before the procedures are illustrated and described, the roles identified to support the identified procedures are illustrated. These roles are depicted as swim lanes within the process flow models.

# Business Process Decomposition

- The business process decomposition represents all the modelled work to be performed within the NDP organisation. This business process model was developed based on a relative clean slate approach where the objective was not to only incrementally improve existing business processes but to reconsider mission effectiveness and only thereafter process efficiency. On the highest level three generic process areas were proposed namely Unit Management, Core and Unit Support processes. Unit Management and Support processes were not further analysed as these are generic processes applicable to the entire NT. If the effectiveness / efficiency of these processes are to be questioned it should be directed to the relevant process owners within NT. The NDP is the process owner of only NDP core processes. These are the processes which are unique to the NDP mandate. Within the NDP Core business processes a business process owner was identified for each of the Core sub processes. These business process owners are ultimately responsible for the completeness, accuracy and currency of all Core business processes. Process owners are as follows:

  - Plan Programme A – Collins Sekele

  - Plan Programme B – David Van Niekerk / Collins Sekele

  - Manage Precincts – David Van Niekerk

  - Implement Programme – Irene Sinovich

  - Monitor Programme – Suzette Pretorius / Irene Sinovich

  - Grant Financial Management – Suzette Pretorius

  - Innovation and Mainstreaming – David Van Niekerk

Figure 1: NDP Business Processes (To Be)

- In order to interpret the two types of models used within every procedure consider the following guidelines:

  - All procedure scopes are represented by an activity model which can generically be illustrated as follows:

Figure 2: Procedure Scopes

  - Within these activity models the following definitions are applicable:

    - Activities represent real world functions. In a function model, activities are graphically shown as boxes and described by active verb phrases. Activities usually have concepts attached to them that describe what resources (controls, and mechanisms) the activity requires to produce the output or set of outputs. An activity must have at least one control attached to it for a method compliant diagram.

    - Inputs are resources consumed by or transformed by activities in the production of outputs. An input is represented by an arrow attached to the left side of an activity box.

    - An output is produced by an activity according to the resources (inputs, controls, and mechanisms) used by the activity. An output is represented by an arrow attached to the right side on an activity box.

    - A control is a resource, manufacturing guidelines for example, that constrains or guides an activity's production of outputs. A control is represented by an arrow attached to the top of an activity box.

    - Mechanisms are resources, such as employees or machines that are used by activities in producing an output. A mechanism is represented by an arrow attached to the bottom of an activity box.

  - More detail of each activity is captured in procedure models which can generically be illustrated as follows:

Figure 3: Example Diagram

# Identified Roles

- The following roles were identified as having specific responsibilities and to be accommodated within the core business structure of NDP. Quantities should be determined after work measurement / estimates and the application of applicable structuring principles.

Figure 4: NDP Core Business Roles

# Procedures

## Procedure Name: Advertise the Grant

- Procedure Scope: Advertise the Grant

Figure 5: Procedure Scope: Advertise the Grant

- Process Aim: To ensure that the process of inviting municipalities to apply for the NDPG is transparent and fair.

- Procedure Model: Advertise the Grant

Figure 6: Procedure Model: Advertise the Grant

Table 1: Advertise the Grant

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Strategic Project Specialist | Collate NDP Grant Advertisement Content - Collate information based on an instruction from the Chief Director - Include the applicable assessment criteria - Revise an application form that need to be populated – only if necessary - Include all the relevant information and conditions of the process as well as information of the Business Support Manager. | There must be unallocated NDP grant funding available. | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities |
| Strategic Project Specialist | Submit NDP Grant Advertisement Content - Ensure approval of the content before forwarding to the Business Support Manager for processing - Forward the content to the Chief Director for approval |  |  |
| Chief Director | Approve NDP Grant Advertisement Content - Sign-off the necessary advertising content submitted by the specialist - Forward to the Business Support Manger for processing |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities |
| Business Support Manager | Prepare Draft NDP Grant Advertisement - Package the advertising content in the correct format before submitting to Finance for processing - Ensure that the sign-off version is the one packaged according to the advertising requirement - Forwards to the Chief Director for final sign off - Forwards the packaged information to the supply chain unit for advertising |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities |
| Business Support Manager | Submit Draft NDP Grant Advertisement - Submission of the packaged advert content to supply chain manage - Email follow ups with supply chain to ensure that all relevant requirements of the advertisement are collated and publicised timeously |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\correspondences with supply chain |

## Procedure Name: Assess Municipal Applications

- Procedure Scope: Assess Municipal Applications

Figure 7: Procedure Scope: Assess Municipal Applications

- Process Aim: To ensure that only municipalities that meet the NDPG criteria are the beneficiaries of the grant.

- Procedure Model: Assess Municipal Applications

Figure 8: Procedure Model: Assess Municipal Applications

Table 2: Assess Municipal Applications

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Admin Assistant | Register the Grant Application - Collect the submitted application forms after the closing date from supply chain management - Ensure that the submitted application forms are stamped (by supply chain), recorded and filed on the appropriate folder - Register all submitted application forms - The relevant Projects Director informed about the submissions - Forward the list to Chief Director |  | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\submitted applications forms\year |
| Chief Director | Allocate Project Director - The Chief Director allocates the new applications to the relevant PD to evaluate |  |  |
| Project Director | Evaluate Grant Application - Check the application against the template - Apply the assessment criteria as per the template - Make recommendations about acceptance or rejection - Package the recommendations in a yellow file | Benchmark: TA not more than 10% of grant value ; minimum R1m | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\submitted applications forms\year |
| Project Manager | Obtain Additional Grant Application Information - Generate a list of information not included in the application - Form - Draft a letter to the municipality requesting missing information |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\additional information requested\year |
| Project Director | Verify Application with Municipal Situation - Site verification visits - Populate the site verification template |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\verification report forms\year |
| Project Director | Recommend Grant Application - Draft a recommendation letter - letter packaged in a yellow folder to the CD for signature - Submit recommendation letter to the CD for signature |  |  |
| Chief Director | Approve Grant Application - Award letter signed as an approval - The PA to sign the letter and file on the I drive - The letter to be emailed to the municipality by the PM and posted by the PA |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Project\award reference\township\1. Funding Agreement |
| Project Director (Propose that this section be deleted) | Draft Notification Letter - Forward the letter to the Projects Manager - Scan the letter on the I drive - The projects manager to email the letter to the municipality |  |  |

## Procedure Name: Formalise the Funding Agreement

- Procedure Scope: Formalise the Funding Agreement

Figure 9: Procedure Scope: Formalise the Funding Agreement

- Process Aim: To formalise the relationship of the NDP Unit and recipients of the grant.

- Procedure Model: Formalise the Funding Agreement

Figure 10: Procedure Model: Formalise the Funding Agreement

Table 3: Formalise the Funding Agreement

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Customise the Funding Agreement - Collate the different schedules into one document - Populate appropriate section of the relevant schedules with relevant available information - Include signed award approval letter |  |  |
| Projects Admin | Obtain Municipal Signature - Letter and collated schedules mailed to the municipality for signature - Follow up with a phone call to ensure that the municipality has received the information |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\3. Correspondence |
| Project Director | Sign Funding Agreement - Original, signed FA is received by PM via post or courier - Check for completeness and revert to municipality if not complete. - If complete, forward to CD - Updates the MIS with the relevant information |  | Funding Agreement Signed by Municipality |
| Chief Director | Sign Funding Agreement - Signs the relevant schedule - Gets witnesses signature - Forward the signed document to the Projects Admin - PA scans the signed document, save it under the i-drive and file the hard copy according to the file plan. - PA forwards the document to the Projects Director who emails the signed document to the municipality |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Funding Agreement |

## Procedure Name: Review Operational Guide for Municipalities

- Procedure Scope: Review Operational Guide for Municipalities

Figure 11: Procedure Scope: Review Operational Guide for Municipalities

- Process Aim: To ensure improved performance of the Neighbourhood Development Partnership Grant (NDPG) in municipalities and their compliance the NDP requirements and conditions of the grant. It is also to standardise the internal operation procedures of the NDP unit.

- Procedure Model: Review Operational Guide for Municipalities

Figure 12: Procedure Model: Review Operational Guide for Municipalities

Table 4: Review Operational Guide for Municipalities

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Strategic Project Specialist | Analyse the Performance / Compliance Deviation - Analyse the reporting trends , content and frequency of the municipalities in accordance with the award performance guidance and as per DORA requirements and the Funding Agreement - Review the processes and structure followed by the municipality in implementing the NDPG programme - An award performance assessment report should be produced at the end of every quarter - Review the BPs and PPs approved by the NDP for implementation by the municipalities - Consider any innovation products that may be contained in the BPs and how they may be mainstreamed in other areas. - Produce a report on possible innovation products and mainstreaming | - Quarterly | - I:\BR_Budget Office\4.CD_NDPG\2 Own\1. Bernadette\BERNIE'S 2010 2011 stuff |
| Strategic Project Specialist | Formulate Solution to Deviation - Review and revise the current toolkit and guidance notes to consider the findings of the performance assessment report - Circulate the proposed amendments to the toolkit and guidance notes to the entire unit for comments - Circulate the proposed revised changes to relevant stakeholders and municipalities for comments |  | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Strategic Project Specialist | Present Solution - Incorporate the comments into the revised toolkit and guidance notes - Forward the final document to the Chief Director for signature |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Chief Director | Approve Reviewed Operational Guide for Municipalities - The revised toolkit packaged and submitted to the Chief Director for signature - Ensure that only final documents are placed on the I drive and the NDP website |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |

## Procedure Name: Induct Municipal Officials

- Procedure Scope: Induct Municipal Officials

Figure 13: Procedure Scope: Induct Municipal Officials

- Process Aim: To ensure that municipal officials understand the requirements of the NDPG and how it functions.

- Procedure Model: Induct Municipal Officials

Figure 14: Procedure Model: Induct Municipal Officials

Table 5: Induct Municipal Officials

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Notify Municipality of Induction - Inform the municipality to arrange the induction workshop through an email - Inform the municipality of the officials that need to be part of the induction workshop | - The 1st induction - within seven days after the Award Status letter has been forwarded to the municipality - The second induction - within seven days after the signing of the Funding Agreement | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\3. Correspondence |
| Project Manager | Prepare Induction Pack - Prepare the agenda of the induction session workshop - The presentation have to be send to the municipality 2 days before the induction - Overview and Funding Agreement induction pack presentation - Administration and reporting/ Management of the Project Stages presentation - Customise the available induction pack presentation – induction packs, 1,2,3 - Induction workshop presentations to be saved on the I drive |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Project Manager | Request Logistic Support - Prepare a travel motivation plan and attached confirmed induction workshop date - Email the travel motivation plan to the Projects Administrator | - The travel motivation plan to be submitted 3 days prior to travelling time | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\Expenditure Tracker 2012 - 2013 |
| Project Manager | Conduct Induction - Presentation at municipalities - Presentation to municipal officials |  |  |
| Project Manager | Obtain Induction Report - Request the induction report from the municipality |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Reports |

## Procedure Name: Validate Service Provider

- Procedure Scope: Validate Service Provider

Figure 15: Procedure Scope: Validate Service Provider

- Process Aim: To ensure that the municipality secures a service provider that will be able to produce deliverables required by the NDP.

- Procedure Model: Validate Service Provider

Table 6: Validate Service Provider

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Project Director | Analyse TOR Request - Review the letter from the municipality requesting assistance with the drafting of the TOR - The letter must be signed by the accounting officer or the NDPG designated signatory - The customise TOR should be in accordance to the NDPG phase within the municipality - Customise the existing TOR from other municipalities to align with the request |  | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\11. Reports |
| Project Manager | Provide a TOR - Email the TOR to the municipality for comments - Request the municipality to confirm TOR through an email and save the email on the I drive - Ensure that the municipal comments are colour coded - Review the revised |  | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence\Confirmations |
| Project Manager | Review Revised TOR - Email the TOR to the PD for final comments - Ensure that the TOR are converted into the PDF before being forwarded to the municipality - Review the comments and ensure that they are incorporated into the TOR - Save the PDF converted file on the I drive |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\11. Reports |
| Project Director | Attend SP Evaluation Committee - Review a letter from the municipality requesting an NDP official to be part of the tender specification committee - Ensure that the request is signed by the accounting officer or the NDPG signatory - Review a letter from the municipality requesting an NDP official to be part of the technical evaluation committee - Get all the dates of the committees - Attend the various committees |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence\Confirmations |
| Project Director | Confirm Recommendations of Evaluation Committee - Obtain recommendations of the evaluation committee from the municipality before they are forwarded to the adjudication committee - Inform the municipality in writing that the recommendations of the evaluation committee should be forwarded to the NDP - Ensure that they are in accordance with the discussions during the evaluation period - Forward a letter to the municipality indicating the NDP position on the recommendations |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Legal |
| Project Administrator | Capture SP Detail - Scan and Save the appointment letter of the service provider on the I drive - Scan and Save the SLA on the I drive - Forward information of the service provide to finance to capturing the details |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\legal |

## Procedure Name: Scope Programme

- Procedure Scope: Scope Programme

Figure 16: Procedure Scope: Scope Programme

- Process Aim: To ensure that there is initial agreement on how the work should be done.

- Procedure Model: Scope Programme

Figure 17: Procedure Model: Scope Programme

Table 7: Scope Programme

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Assess the Status Quo - Does the Status Quo Report assess the overall status of the areas within which the proposed interventions will take place on a district, municipal vs township scale including: - Development Context (location, history, social, economic, physical and natural environment) - Demographics - Key developmental challenges - Target beneficiary groups - Any spatial and non-spatial issues? - Assess the status quo in accordance with the guidance notes and the status quo assessment template to be developed - Does the status quo assess and prioritise the interventions - Check whether the status quo reviews the municipal capacity - Check whether the status quo scopes the studies required |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\Operations Guide\Operations Guide for Munis\4_Project Preparation |
| Project Manager | Evaluate the TA Workplan - Review the TA work plan - Forward a TA work plan approval letter to the municipality |  | I drive approval documents\ TA work plan |

## Procedure Name: Develop Programme Business Case

- Procedure Scope: Develop Programme Business Case

Figure 18: Procedure Scope: Develop Programme Business Case

- Process Aim: To develop a medium term implementable plan for the municipality.

- Procedure Model: Develop Programme Business Case

Figure 19: Procedure Model: Develop Programme Business Case

Table 8: Develop Programme Business Case

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Assess Sector / Leverage / Nodes - Corridor Plans - Assess the leverage investment potential (potential of the programme to leverage investment, analysis of potential investors and their contributions, a strategy to leverage investment) plans in accordance to the developed guidance nodes and toolkit - Precinct structure development plans - Identification of the primary precinct - Linkages of the primary precinct with other nodes within the area ( existing and proposed) - Linkage of the primary precinct with the established precinct within the region and original CBDs - Make recommendations - Forward the recommendations of the assessment to the Projects Director |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.15 Strategy |
| Project Director | Assess Township Re-generation Strategy (TRS) In assessing in line with the available guidance notes the one will have establish the following: - The overall status of the township and identification of SWOT - Timeframe – it has to be long term - Township focused - Multi-sectoral and visionary - Implementation and prioritisation - Management and monitoring Make recommendations to the Projects Director |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.15 Strategy |
| Project Director | Assess Business Plans - Assessment to be done according to the template |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.15 Strategy |
| Project Manager | Control Execution of TA Work plan - Request monthly progress report from the municipality - Resolve any challenges that delay execution of the TA workplan - Ensure submission of the monthly progress report before any invoices could be processed |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects |

## Procedure Name: Assess Portfolio

- Procedure Scope: Assess Portfolio

Figure 20: Procedure Scope: Assess Portfolio

- Process Aim

- Procedure Model: Assess Portfolio

Figure 21: Procedure Model: Assess Portfolio

Table 9: Assess Portfolio

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Strategic Support | Identify Urban Municipalities |  | Density Maps COGTA Classification |
| Specialist Strategic Support | Categorise Municipal Funding | Rules?? |  |
| Specialist Strategic Support | Identify Non Funded Townships |  |  |
| Specialist Strategic Support | Apply Clustering Model |  |  |
| Specialist Strategic Support | Identify Neighbourhood Hub Location |  | Neighbourhood Hub Location |

## Procedure Name: Allocate Award

- Procedure Scope: Allocate Award

Figure 22: Procedure Scope: Allocate Award

- Process Aim

- Procedure Model: Allocate Award

Figure 23: Procedure Model: Allocate Award

Table 10: Allocate Award

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Admin Asst | Register Grant Allocation |  |  |
| Chief Director | Allocate Project Director | Rules? |  |
| Project Director | Present Grant Allocation |  | Grant Presentation |
| Project Director | Recommend Grant Allocation | Rules? | Accepted Grant Allocation Non Accepted Grant Presentation Non Acceptance Report |
| Chief Director | Approve Grant Allocation | Rules? | Award Letter |

## Procedure Name: Formalise the Funding Agreement

- Procedure Scope: Formalise the Funding Agreement

Figure 24: Procedure Scope: Formalise the Funding Agreement

- Process Aim: To formalise the relationship of the NDP Unit and recipients of the grant.

- Procedure Model: Formalise the Funding Agreement

Figure 25: Procedure Model: Formalise the Funding Agreement

Table 11: Formalise the Funding Agreement

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Customise the Funding Agreement - Collate the different schedules into one document - Signed award approval letter attached - Populate appropriate section of the relevant schedules with relevant available information - Collated schedules with relevant information populated - Include award approval letter |  |  |
| Projects Admin | Obtain Municipal Signature - The PM to email the information to the municipality - Letter and collated scheduled mailed to the municipality for signature - Follow up with a phone call to ensure that the municipality has received the information |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\3. Correspondence |
| Chief Director | Sign Funding Agreement - Signature in the relevant schedule - Witnesses signature - Forward the signed document to the Projects Admin - Document scanned ; and hard copy filed |  | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Funding Agreement |

## Procedure Name: Review Operational Guide for Municipalities

- Procedure Scope: Review Operational Guide for Municipalities

Figure 26: Procedure Scope: Review Operational Guide for Municipalities

- Process Aim: To ensure improved performance of the Neighbourhood Development Partnership Grant (NDPG) in municipalities and their compliance the NDP requirements and conditions of the grant. It is also to standardise the internal operation procedures of the NDP unit.

- Procedure Model: Review Operational Guide for Municipalities

Figure 27: Procedure Model: Review Operational Guide for Municipalities

Table 12: Formalise the Funding Agreement

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Strategic Project Specialist | Analyse the Performance / Compliance Deviation - Analyse the reporting trends, content and frequency of the municipalities as per DORA requirements and the Funding Agreement - Review the processes and structure followed by the municipality in implementing the NDPG programme - Review the BPs and PPs approved by the NDP for implementation by the municipalities - Consider any innovation products that may be contained in the BPs and how they may be mainstreamed in other areas. | - The analysis is in accordance with the award performance guidance per quarter - An award performance assessment report should be produced at the end every quarter - Produce a report on possible innovation products and mainstreaming | - I:\BR_Budget Office\4.CD_NDPG\2 Own\1. Bernadette\BERNIE'S 2010 2011 stuff |
| Strategic Project Specialist | Formulate Solution to Deviation - Review and revise the current toolkit and guidance notes to consider the findings of the performance assessment report - Circulate the proposed toolkit and guidance notes to the entire unit for comments - Circulate the proposed revised changes to relevant stakeholders and municipalities for comments | - Revise the toolkit and guidance notes in accordance with the performance assessment report | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Strategic Project Specialist | Present Solution - Incorporate the comments into the revised toolkit and guidance notes - Forward the final document to the Chief Director for signature | - Comments incorporated into the revised documents - Final document forwarded to the Chief Director for signature | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Chief Director | Promulgate Reviewed Operational Guide for Municipalities - The revised toolkit packaged and submitted to the Chief Director for signature | - Ensure that only final documents are placed on the I drive and the NDP website | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |

## Procedure Name: Induct Municipal Officials

- Procedure Scope: Induct Municipal Officials

Figure 28: Procedure Scope: Induct Municipal Officials

- Process Aim: To ensure that municipal officials understand the requirements of the NDPG and how it functions.

- Procedure Model: Induct Municipal Officials

Figure 29: Procedure Model: Induct Municipal Officials

Table 13: Induct Municipal Officials

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Notify Municipality of Induction - Inform the municipality to arrange the induction workshop through an email - Inform the municipality of the officials that need to be part of the induction workshop | - The 1st induction should be within seven days after the Award Status letter has been forwarded to the municipality - The second induction should be within seven days after the signing of the Funding Agreement | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\3. Correspondence |
| Project Manager | Prepare Induction Pack - Prepare the agenda of the induction session workshop - Customise the available induction pack presentation – induction packs, 1,2,3 | - Overview and Funding Agreement induction pack presentation - Administration and reporting/ Management of the Project Stages presentation - The presentation have to be send to the municipality 2 days before the induction - Induction workshop presentations to be saved on the I drive | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.4 Induction Pack |
| Project Manager | Request Logistic Support - Prepare a travel motivation plan and attached confirmed induction workshop date - Email the travel motivation plan to the Projects Administrator | - The travel motivation plan to be submitted 3 days prior to travelling time | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\Expenditure Tracker 2012 - 2013 |
| Project Manager | Conduct Induction - Presentation at municipalities | - Presentation to municipal officials |  |
| Project Manager | Obtain Induction Report - Request the induction report from the municipality | - Request the report from the municipality | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Reports |

## Procedure Name: Validate Service Provider

- Procedure Scope: Validate Service Provider

Figure 30: Procedure Scope: Validate Service Provider

- Process Aim: To ensure that the municipality secures a service provider that will be able to produce deliverables required by the NDP.

- Procedure Model: Validate Service Provider

Figure 31: Procedure Model: Validate Service Provider

Table 14: Validate Service Provider

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Project Director | Analyse TOR Request - Review the letter from the municipality requesting assistance with the drafting of the TOR - Customise the existing TOR from other municipalities to align with the request | - The request letter should be signed on the I drive by the PA - The letter must be signed by the accounting officer or the NDPG designated signatory - The customise TOR should be in accordance to the NDPG phase within the municipality | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\11. Reports |
| Project Manager | Provide a TOR - Email the TOR to the municipality for comments - Review the revised | - Request the municipality to confirm TOR through an email and save the email on the I drive - Ensure that the municipal comments are colour coded | - I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence\Confirmations |
| Project Manager | Review Revised TOR - Review the comments and ensure that they are incorporated into the TOR | - Email the TOR to the PD for final comments - Ensure that the TOR are converted into the PDF before being forwarded to the municipality - Save the PDF converted file on the I drive | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\11. Reports |
| Project Director | Attend SP Evaluation Committee - Review a letter from the municipality requesting an NDP official to be part of the tender specification committee - Review a letter from the municipality requesting an NDP official to be part of the technical evaluation committee - Attend the various committees | - Ensure that the request is signed by the accounting officer or the NDPG signatory - Get all the dates of the committees | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\WRD400\4_135.2_West Rand_WRTRI\3. Correspondence\Confirmations |
| Project Director | Confirm Recommendations of Evaluation Committee - Obtain recommendations of the evaluation committee from the municipality before they are forwarded to the adjudication committee - Ensure that they are in accordance with the discussions during the evaluation period - Forward a letter to the municipality indicating the NDP position on the recommendations | - Inform the municipality in writing that the recommendations of the evaluation committee should be forwarded to the NDP | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\Legal |
| Project Administrator | Capture SP Detail - Save the appointment letter of the service provider on the I drive - Save the SLA on the I drive | - Scan the appointment letter to the I drive - Scan the SLA and save on the I drive - Forward information of the service provide to finance to capturing the details | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\municipal reference\township\award reference number\legal |

## Procedure Name: Scope Programme

- Procedure Scope: Scope Programme

Figure 32: Procedure Scope: Scope Programme

- Process Aim: To ensure that there is initial agreement on how the work should be done.

- Procedure Model: Scope Programme

Figure 33: Procedure Model: Scope Programme

Table 15: Scope Programme

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Assess the Status Quo - Does the Status Quo Report assess the overall status of the areas within which the proposed interventions will take place on a district, municipal vs township scale including: - Development Context (location, history, social, economic, physical and natural environment) - Demographics - Key developmental challenges - Target beneficiary groups - Any spatial and non-spatial issues? - Does the status quo assess and prioritise the interventions - Check whether the status quo reviews the municipal capacity - Check whether the status quo scopes the studies required | - Assess the status quo in accordance with the guidance notes and the status quo assessment template to be developed | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\Operations Guide\Operations Guide for Munis\4_Project Preparation |
| Project Manager | Evaluate the TA Workplan | - Forward a TA work plan approval letter to the municipality - Forward the | I drive approval documents\ TA work plan |

## Procedure Name: Develop Programme Business Case

- Procedure Scope: Develop Programme Business Case

Figure 34: Procedure Scope: Develop Programme Business Case

- Process Aim: To develop a medium term implementable plan for the municipality.

- Procedure Model: Develop Programme Business Case

Figure 35: Procedure Model: Develop Programme Business Case

Table 16: Develop Programme Business Case

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Director | Assess Neighbourhood Hub Location | Rules?? | Neighbourhood Hub Location Approval Letter |
| Project Director | Assess Neighbourhood Hub Precinct Design | Rules?? |  |
| Project Director | Assess Business Plans~ | Rules?? | Business Plan Innovation Opportunities Business Plan Approval Letter |
| Chief Director | Approve Business Plans |  |  |
| Project Director | Control Execution of TA Workplan |  | Municipal Progress Report Portfolio Report |

## Procedure Name: Manage Precincts

- Procedure Scope: Manage Precincts

Figure 36: Procedure Scope: Manage Precincts

- Process Aim

- Procedure Model: Manage Precincts

Figure 37: Procedure Model: Manage Precincts

Table 17: Manage Precincts

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Project Director | Evaluate BID (Business Improvement District) Formation Plan |  | BID (Business Improvement District) Formation Plan Referral |
| Chief Director | Approve BID (Business Improvement District) Formation Plan |  | Approved BID (Business Improvement District) Formation Plan Pipelined NDP Projects |

## Procedure Name: Review / Approve Project Plans

- Procedure Scope: Review / Approve Project Plans

Figure 38: Procedure Scope: Review / Approve Project Plans

- Process Aim

- Procedure Model: Review / Approve Project Plans

Figure 39: Procedure Model: Review / Approve Project Plans

Table 18: Review / Approve Project Plans

| Responsibility | Activity Description | Decision Rules | Quality records (QRs) |
| --- | --- | --- | --- |
| Project Finance Specialist | Evaluate Project Economic and Financial Feasibility To determine whether the project has - sufficient and realistic leverage targets, - whether the budgeted amounts are in line with benchmarked amounts - whether the requisite M&O funds have been planned for - whether the necessary feasibility studies e.g. economic viability and rental/ accommodation studies have been done bearing in mind the various inputs as noted above (muni segmentation, state of local government etc.) Review considerations: Are adequate information on costs provided (broad planning and capital investment costs)? Are costs realistic and has it been substantiated (eg. Provisional Bill of Quantities)? Are financial calculations correct? Are proposed NDPG costs within the approved programme limit? (If applicable) Are proposed NDPG costs within the approved funding envelope limit? Are CG calculations VAT exclusive? Are contingencies and escalation included in the Project Plan Costs? Are the annual allocations published adequate to support the cash-flow scenario? Does the project show commitment to leverage? Is the leverage proposed within the Project Plan in line with leverage proposed within the Business Plan? Is the leverage proposed within the Project Plan in line with leverage proposed within the Funding Agreement? Is the extent to which external funds have been secured explained/proof of commitment provided? Does the Municipality have confirmed plans for operations and maintenance of the project? Has asset ownership been agreed by the Municipality? Is the medium to long term financial viability of the project illustrated within the Project Plan? Is a dedicated person from the Municipality responsible for the Close-Out Report? Does the project illustrate how employment will be created? To do and/or asses a multi-year RoI study, Socio-Economic Assessment |  | Submitted Project Plan I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\Operations Guide\Operations Guide for Munis\4_Project Preparation\4.3_Business and Project Plans\4.3.3_ProjectPlan_Template_Dec10.xlsm Project Plan Referral Letter As specific format has to be developed M&O study and/or supporting studies e.g. feasibility study, Submissions from municipality is filed at I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\3 digit acronym& new number\Old ref number\11. Reports Recommendation to PD Currently on MIS – may need to be developed further Please note that there is a new PP format – SuPr to provide |
| Project Manager | Evaluate Project Plan Sustainability & Concept To determine whether the plan is in line with - the NDP guidelines and prescripts - whether the plan is NDPG compliant, - whether there is causal and logical flows between strategy and plan, - whether the broader concept fits into other existing plans and strategies of the municipality. Considerations: Does the project broadly align to the NDP? Is the project a Municipal priority (confirmed in IDP, SDF, Council Resolution)? Confirm whether the supporting documentation provides sufficient insight to understand the context of the project? The project is well motivated and clearly illustrates the reason/s, need for and objectives for the project? Does the project clearly illustrate alignment with the Business Plan and/or TRS and/or alternative overarching plan should the Business Plan not yet exist? Will the project stimulate township regeneration and improve the quality of life of its inhabitants? Will the project be catalytic for other investment and economic development? Does the project plan illustrate the readiness of the project to start capital expenditure? (resource requirements agreed, partnership structures in place, agreements and/or guarantees in place etc) Are Timelines realistic (eg. time for construction of a building aligned to industry benchmarks)? Does the sequencing of products make sense? Has design sign-off and asset ownership been agreed by the Municipality? Are there any high level risks associated with this section? Will the mitigating measures be sufficient to address the risk/s? |  | Submitted Project Plan I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\Operations Guide\Operations Guide for Munis\4_Project Preparation\4.3_Business and Project Plans\4.3.3_ProjectPlan_Template_Dec10.xlsm Project Plan Referral Letter As specific format has to be developed M&O study and/or supporting studies e.g. feasibility study, Submissions from municipality is filed at I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\3 digit acronym& new number\Old ref number\11. Reports Recommendation to PD Currently on MIS – may need to be developed further Please note that there is a new PP format – SuPr to provide |
| Project Director | Approve Project Plan To verify that all compliance measures have been verified and that the economic feasibility and sustainability concept evaluation makes sense/ are technically sound/ shows verifiable logic. Project plan approval criteria are - Project Motivation (Alignment to NDP) - Implementability - Project Financials - Leverage - Completion and Sustainability - Risk Management - Innovation criteria -To be developed |  | Approved Project Plan MIS Innovation Opportunities record To be developed Pipelined NDP Projects SuPr to advise methodology |
| Project Manager | Draft Project Approval Letter Standard letter to be drafted as per template. MIS figures and financial data on letter to be the same. |  | Project Approval Letter I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.2 Templates\Business Plan Pack\06 NDP Business and-or Project Plan Approval Letter Template.doc Project Plan Rejection Letter Generally the same Template as per Approval letter is used with modifications but it may need to be developed specifically |

## Procedure Name: Close Out Project

- Procedure Scope: Close Out Project

Figure 40: Procedure Scope: Close Out Project

- Procedure Model: Close Out Project

Figure 41: Procedure Model: Close Out Project

Table 19: Close Out Project

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Compare Close Out Report with Project Plan To determine - whether the objectives have been achieved - final costings are aligned with initial cost estimates, if not to update PP approval value - Check for completeness. |  | Project Close Out Report Old version: I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\Business and Project Plans Approval Process\CloseOutTemplate_15Nov10_Ver1.xls |
| Project Manager | Identify Innovation Opportunities Projects that exhibit high levels of Partnership, Innovation, Equity and Community needs to be highlighted - ‘tick list’ of projects that possible fall into this category needs to be developed | Identify | Innovation Opportunities record To be developed |
| Project Manager | Determine Compliance Not sure what this was meant to be? Seems the same as compare and id innovation | Compare Identify Comply | If not compliant – need to develop remedial measures |
| Project Director | Revise PP Value Detailed description provided in SOP: I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\SOP Adjustment of Project Approval Amounts 20120124.doc | Revise approval letter | PP value amendment SOP I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\SOP Adjustment of Project Approval Amounts 20120124.doc Updated Approval Letter I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.2 Templates\Business Plan Pack\06 NDP Business and-or Project Plan Approval Letter Template.doc |
| Team Asst | File Close Out Report in terms of filing plan else to be uploaded to MIS at Supporting Documents (upload area to be created) | Report files in correct place | Filed Close Out Report Three digit acronym, round no\original award number\ municipal name\ programme name\11. Reports e.g. I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\ BIT400\4_069_Bitou_Bitou Coming Together\11. Reports |

## Procedure Name: Review BP / Programme

- Procedure Scope: Review BP / Programme

Figure 42: Procedure Scope: Review BP / Programme

- Procedure Model: Review BP / Programme

Figure 43: Procedure Model: Review BP / Programme

Table 20: Review BP / Programme

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Compare Exit Report with FA and BP Exit report format has apparently changed (Aurecon) – template may or may not include areas for ‘comparison’ , else these fields need to be determined. |  | Programme Exit and Review Report New format – SuPr to provide Returned Programme Exit and Review Report Old format: I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\Business and Project Plans Approval Process\ExitReviewAssessmentReport_13Nov10_Ver1.xls |
| Project Director | Identify Innovation Products Projects that exhibit high levels of Partnership, Innovation, Equity and Community needs to be highlighted - ‘tick list’ of projects that possible fall into this category needs to be developed | Identify | Innovation Opportunities record To be developed |
| Project Administrator | Update MIS Database Not sure what this will involve – I do not think BP information as approved should be changed, only certain new documents to be uploaded unless a section can be developed where the PM/PD ‘signs off” or gives final comments | Update where changes occurred | MIS |
| Project Administrator | File Exit Report in terms of filing plan else to be uploaded to MIS at Supporting Documents (upload area to be created) | When this activity has been completed, file relevant documents | Signed Award Closure Sheet I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.7 Municipalities\Operations Guide\Operations Guide for Munis\6_Exit\6.3_AwardClosure_Template_Nov09.doc Three digit acronym, round no\original award number\ municipal name\ programme name\11. Reports e.g. I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\ BIT400\4_069_Bitou_Bitou Coming Together\11. Reports |
| Team Asst | Close Municipal Award Close out letter template to be developed with legal opinion on how to terminate contract (funding agreement) | To draft Municipal award closure letter when procedures in this category has been completed. | Municipal award closure letter template to be developed |

## Procedure Name: Monthly Reporting

- Procedure Scope: Monthly Reporting

Figure 44: Procedure Scope: Monthly Reporting

- Process Aim:  To review the monthly reports submitted by the municipalities and ensure corrective action and amendments, where necessary

- Procedure Model: Monthly Reporting

Figure 45: Procedure Model: Monthly Reporting

Table 21: Monthly Reporting

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Administrator | Obtain Monthly Reports Municipalities are informed during induction of deadlines for submission. Track monthly progress report submissions and based on previous submissions remind municipalities to submit who have not submitted or have a bad record of submitting. Normal submission dates are between 5th of the month and 15th. Apart from the monthly progress report, the municipal segmentation as updated on a monthly basis, the portfolio report and planned actions for the month, minutes and decisions of meetings, email correspondence and other communique’s provide valuable inputs to a monthly overview of progress over the past month. Keep track (list) of conditions of PP approvals. | Is progress report submitted? Is cash flow and MPS available? Is conditionalities list updated? | Monthly Reports MIS |
| Project Manager | Analyse Monthly Reports Check whether MIS adds up properly (cumulative from previous months), verify actual spend against cash flows as projected. Unless >80% spent, provide inputs to SP whether CG drawdown should continue or not. Analyse previous months portfolio report for actions to be performed and evaluate against actual work done. Compare delivery on conditionalities stated in PP approval letters to work submitted. |  | Deviation Findings between transferred, spent and cash flows Calculated via MIS (>80% or <80%) – to be developed Updated Municipal Segmentation I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.11 Municipal Segmentation Updated portfolio report – to be developed |

## Procedure Name: Re-align Project Work Plans

- Procedure Scope: Re-align Project Work Plans

Figure 46: Procedure Scope: Re-align Project Work Plans

- Process Aim

- Procedure Model: Re-align Project Work Plans

Figure 47: Procedure Model: Re-align Project Work Plans

Table 22: Re-align Project Work Plans

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Director | Develop Corrective Measures Decide on most appropriate manner in which to deal with non-compliance/ deviations Communicate with municipality – manner depending on corrective measure to be followed, either email, telecom, meeting, formal written correspondence. Presently, the PD’s engage individual municipalities to speed up or slow down projects and/or processes to align with the MPS as submitted. If there is no alignment, withholding letters are sent – later stopping letters if non-compliance continues (SuPret to supply templates) Professional discretion largely used in conjunction with discussions with municipality on what are possible and preferred adjustments to be made. Usually as per meeting held and minutes drafted. |  | Templates and formats to be developed. Project meeting minutes Submissions from municipality is filed at I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\3 digit acronym& new number\Old ref number\4. Meetings e.g. I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\BFW400\4_029_Beaufort West_Urban Nodal Development\4. Meetings Project Implementation Advice – standard format to be determined Withholding and/or stopping letters – process links to SuPr process to IGR – SuPr to provide latest templates (template not found on I drive) I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.3 Financial & Management Info\6.3.19 Back up all years\20. Suzette\Actual DORA reporting\201112 year\Payments schedule\withhold request to IGR for more than 90 days - revised.doc Example: I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.10 Portfolio\6.10.5 NDPG Projects\LGB400\4_018_Langeberg_Robertson Township Initiative\8. Capital Grant\4_018_Langerberg_CG withholding Letter_16 March 2012.doc |
| Project Director | Amend Project Plan Values Implement SOP guidelines. Detailed description provided in SOP: I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\SOP Adjustment of Project Approval Amounts 20120124.doc | Revise approval letter | PP value amendment SOP I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.3 Workflow\SOP Adjustment of Project Approval Amounts 20120124.doc Updated Approval Letter I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.14 Standard\6.14.2 Templates\Business Plan Pack\06 NDP Business and-or Project Plan Approval Letter Template.doc |
| Project Manager | Obtain Revised Project Work Plan Request revised work plan and cash flows. May need to resubmit MPS: Suz to advise process within IGR to make this possible, if possible | No decisions – to be uploaded on MIS | Revised cash flows and MPS MIS |
| Project Manager | Develop Portfolio Reports The data as provided by municipalities, the deviation reports and ‘to do’ will be consolidated into a portfolio report via an automated process. | None – automated process | Portfolio Report New format under discussion between DvN to finalise |

## Procedure Name: Segment Municipalities

- Procedure Scope: Segment Municipalities

Figure 48: Procedure Scope: Segment Municipalities

- Process Aim: To engage with municipalities and based on their segmented profile and ensure corrective ways of action.

- Procedure Model: Segment Municipalities

Figure 49: Procedure Model: Segment Municipalities

Table 23: Segment Municipalities

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Rate Municipal Performance | Rules?? |  |
| Project Director | Update Municipal Segmentation |  | Updated Municipal Segmentation |

## Procedure Name: Municipal Performance Protocol

- Procedure Scope: Municipal Performance Protocol

Figure 50: Procedure Scope: Municipal Performance Protocol

- Process Aim

- Procedure Model: Municipal Performance Protocol

Figure 51: Procedure Model: Municipal Performance Protocol

Table 24: Municipal Performance Protocol

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Project Manager | Verify Information | Rules?? |  |
| Project Director | Perform Assessment | Rules?? | Recommendation |
| Project Director | Determine Areas of Non Performance | Rules?? |  |
| Project Director | Notify Municipality of Performance Outcome |  | Assessment Notification Letter |
| Project Director | Conduct Information Session |  | Request for Remedial Plan |
| Project Director | Assess Remedial Plan | Rules?? | Remedial Plan Rejected Remedial Plan |
| Project Director | Monitor Municipal Progress |  | Municipal Progress |
| Project Director | Terminate Funding Agreement | Rules?? | Grant Termination Letter |
| Project Director | Move to Grant Management | Rules?? | Re-Activated Award |

## Procedure Name: Prioritise Pipelined Projects

- Procedure Scope: Prioritise Pipelined Projects

Figure 52: Procedure Scope: Prioritise Pipelined Projects

- Process Aim: The purpose of this process is to have an overview of all submitted projects in the NDPG, whether approved or not approved as well as the stage that every project is in. This produces a pipeline (registry) of projects, prioritised according to certain criteria, that is used during different events of the NDP life cycle.

- Procedure Model: Prioritise Pipelined Projects

Figure 53: Procedure Model: Prioritise Pipelined Projects

Table 25: Prioritise Pipelined Projects

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance | Request updated cash flows from municipalities Specialsit Finance request the project teams to ask for updated cash flows for their projects | 10 Sept – 10 Oct |  |
| Specialist Finance | Obtain Pipeline Report The Specialist Finance obtains a pipeline report from the MIS. | 15 October | Cash Flow Forecast Submitted NDP Projects |
|  | Review Pipeline Prioritisation This report is reviewed as follows: - By NDP Finance for accuracy and completeness of data - By the project portfolio’s for to agree with the prioritisation and or highlight any concerns - By the function that needs the report as input into a decision making process Pipeline criteria - Project status: Approved vs Not approved (submitted) - On-the ground ; tender phase ; approved ; - Urban / Rural - Municipal segmentation - Predicted Cash flow value | 16 – 30 October | Prioritised Pipelined Report |

## Procedure Name: MTEF Budget

- Procedure Scope: MTEF Budget

Figure 54: Procedure Scope: MTEF Budget

- Process Aim: The purpose of this process is to have the NDPG’s final 3 year budget figures confirmed with Corporate Services to finalise the municipal in-line allocations that needs to balance to these bottom line figures.

- Procedure Model: MTEF Budget

Figure 55: Procedure Model: MTEF Budget

Table 26: MTEF Budget

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Chief Director | Workshop Programme Forecast Chief Director attends the Programme Forecast and review meeting and presents information based on the strategy agreed in the NDP Strategic planning workshop held in February of every year. | May every year | None – presentation form CD with proposed/ indicative MTEF numbers |
| Chief Director | Workshop Annual Performance Review and Forecast Chief Director sets up the annual performance review and MTEF budget meeting This workshop - provides feedback and KPI review of the previous year - Discusses the situational / external environment changes that will impact the budget and operational procedures of the unit over the next 3 years - agrees the budgeting principles for the next MTEF period (starting the following year on 01 April) - highlights any gaps / concerns that needs to be addressed during the budget period over the next 3 months Reviews the pipelined projects in alignment with the above criteria and sets plan of action for aligning projects with budget plan. | Within the first week of July | MTEF Instruction(email from Corp Services) |
| Specialist Finance | Submit Adjusted Bottom Line Forecast for MTEF The Finance Specialist prepares the bottom line figures (1 for TA and 1 for CG) per year for the forthcoming MTEF / 3 year period. The Chief director reviews the allocation. If he is satisfied, he forwards the submission to Corporate Services. If not, he sends it back to the Finance Specialist for review. (In November, Corporate Services sends letters to all departments with their confirmed bottom line allocations for the MTEF periods as signed off by the CFO: NT) | This is usually due in the last week of July of every calendar year | Submitted MTEF Bottom Line Allocation Confirmed MTEF Bottom line Allocation |
| Specialist Finance | Evaluate MTEF Municipal Projections Specialist Finance pulls an updated pipeline report with the prioritised projects and derives cut off amount that aligns with the bottom line figures Specialist Finance forwards the portfolio allocations to the project directors for note and final comments Final comments received from PD’s and worked into final detail allocation proposal. | - 10 Nov | Confirmed MTEF Bottom Line Allocation (letter example on I drive) |
| Chief Director Specialist: Finance | Consolidate MTEF Municipal Projections Chief Director receives the Confirmed MTEF Allocation letter from Corporate services Letter is saved on i-drive by Business Support Manager and hard copy filed. CD informs Specialist Finance of the letter. Specialist Finance Reviews the values and notes any discrepancies from what was submitted. Finance submits to CD for final approval | 15 November | Confirmed MTEF Bottom Line Allocation (letter example on I drive) |
| Chief Director | Review MTEF Municipal Projections Specialist Finance prepares submission to IGR CD signs off final allocations | Allocations may only be rounded off to R’000 | MTEF Allocation Letter |
| Chief Director Specialist Finance | Submit Final Municipal MTEF Allocation Specialist Finance submits the MTEF allocation to Corporate Services and IGR. |  | Approved MTEF Budget |

## Procedure Name: In Year Budget

- Procedure Scope: In Year Budget

Figure 56: Procedure Scope: In Year Budget

- Process Aim: The purpose of this process is to have the NDPG’s final in- year budget figures confirmed with Corporate Services to finalise the municipal in-line allocations that needs to balance to this bottom line figure.

- Procedure Model: In Year Budget

Figure 57: Procedure Model: In Year Budget

Table 27: In Year Budget

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Chief Director | In Year Workshop Annual Performance Review and Forecast This workshop follows the ‘Workshop Annual Performance Review and Forecast’ and focuses on the In-Year budget specific. This meeting addresses the following: - Review of current projects on the ground - Review of pipeline projects - Any movements between TA and CG Risks and other measures to meet the budget. | Adjustments necessary for in year allocation | In Year Budget Instruction |
| Specialist Finance | Submit Adjusted Bottom Line Forecast for In Year Specialist Finance prepares adjusted in year allocations based on pipeline report and inputs from workshop Finance forwards the data to the CD: NDP to submit to Corporate Services | 1 – 8 Aug | Confirmed In Year Bottom Line Allocation |
| Specialist Finance | Evaluate In Year Municipal Projections Specialist Finance pulls an updated pipeline report with the prioritised projects and derives cut off amount that aligns with the bottom line figures Specialist Finance forwards the portfolio allocations to the project directors for note and final comments Final comments received from PD’s and worked into final detail allocation proposal. Intention to reduce allocation letters compiled by poroject teams and send to CD to sign. Letters sent to municipalities to inform them of the NDP’s intention to reduce their allocation. | 15 – 20 Oct 20 – 28 Oct 30 Oct 31 Oct | Adjusted Estimates for National Expenditure |
| Specialist Finance | Consolidate In Year Municipal Projections Appropriation Bill is tabled in Parliament Specialist Finance request confirmation of bottom line number from Corporate Services Specialist Finance Reviews the values and notes any discrepancies from what was submitted. | Last week October 5 working days after above |  |
| Specialist Finance | Review In Year Municipal Projections Specialist Finance prepares the in year allocation based on the prioritised pipeline report. This report is forwarded to the project teams to note and agree. Finance submits to CD for final approval |  |  |
| Chief Director Specialist Finance | Submit Final Municipal In Year Allocation Specialist Finance submits the final allocations to the Chief Director to sign off. Specialist Finance prepares the final submission of the in year allocation to Corporate Services and IGR. | Rounded to nearest R’000 | Approved In Year Budget Schedule 6&7 Gazette |

## Procedure Name: DORA Payment Schedule

- Procedure Scope: DORA Payment Schedule

Figure 58: Procedure Scope: DORA Payment Schedule

- Process Aim: This process aims to prepare the information to populate the payment schedule and Schedule 3A for the In Year.

- Procedure Model: DORA Payment Schedule

Figure 59: Procedure Model: DORA Payment Schedule

Table 28: DORA Payment Schedule

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance | Request Municipal Cash Flow Specialist Finance confirms the deadlines from IGR relating to the submission of the payment schedule to them (usually first week of May) Specialist Finance writes an email requesting the municipalities to submit their projected cash flows and forwards to the project teams. | As soon as the Dorbill is published (Mid-Feb) | Email |
| Project Administrator | Obtain Project Work Plan / Cash Flow Forward the email from Specialist Finance to the municipalities to submit their project cash flows on MIS for both TA and CG for the new year to start on 01 April. Print the cash flow reports for each municipalities from MIS Ensure that all municipalities that has an allocation for TA and CG in the current year has submitted their cash flows Follow up on the municipalities that has not yet submitted their cash flows Submit all the cash flow reports from different municipalities to the Projects Manager | Due end March. Needs to balance with the gazetted allocation for the year. | Project Work Plan Submission Instruction Cash Flow Request |
| Project Director | Assess Project Work Plan / Cash Flow Assesses the cash flow report for each municipality Ensure the alignment of cash flows with current year allocation for both TA and CG Ensure the alignment of cash flows with approved projects Contact the municipality if further explanations are required Attends a meeting to discuss the cash flows with Specialist Finance and the Chief Director | 1 – 10 April | Cash flow reports from MIS |
| Chief Director | Approve Cash Flow Discuss the cash flows with Projects Director Approve the cash flows submitted by the municipalities Submit the Approved projected cash flows to Specialist Finance | 10 – 15 April | Summary of cash flow reports |
| Specialist Finance | Collate Drawdowns Ensure that the projected cash flows submitted are within the allocations for the year – final check Populate the payments schedule excel sheet received from IGR and send a copy to the project teams to sign off Submit the payments schedule to IGR by email | 16 – 30 April | Cash flow reports for all municipality |
| Specialist Finance | Populate Schedule 3A's Populate Schedule 3A’s from the final payments schedule submitted to IGR | 20 – 25 April | Payments schedule |
| Specialist Finance | Obtain Signoff Schedule 3A's Request Projects Administrator to forward to municipalities for signatures from municipal manager or approved Schedule 4 signatory Signed off 3A’s are collated by the project teams and given to NDP Finance to review and forward to the Chief Director. Submit to Chief Director for sign off Request Projects Administrator to file the signed Schedule 3A’s | End May | Unsigned Schedule 3 A's Filed Schedule 3A |

## Procedure Name: TA Invoice Payment

- Procedure Scope: TA Invoice Payment

Figure 60: Procedure Scope: TA Invoice Payment

- Process Aim – To reimburse the service providers on the work done for NDPG for Technical assistance.

- Procedure Model: TA Invoice Payment

Figure 61: Procedure Model: TA Invoice Payment

Table 29: TA Invoice Payment

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Business Support Manager | Receive Invoice Receive Service Provider tax invoice by a courier or hand delivered by the municipality or service provider. Acknowledge receipt of Service Provider tax invoice by way of a signature Date stamp all documents received from Service Provider Record all documents received on the NDPG receipt book Scan and save all documents received to the I-drive on the relevant project number Alert Project Administrator of tax invoice received | Must be original document. Day of receipt of tax invoice Same day | Service Provider Tax Invoice and supporting documents of work done and disbursements incurred Papertrail and hard copy in filing cabinet |
| Project Administrator | Prepare Invoice Upload and link the tax invoice and supporting documents to Papertrail on the relevant Municipality and project reference number Verify the validity of the claim according to the check list Request more information/ supporting documents if the above requirements are not met Recommend tax invoice payment to the Project Manager | Technical assistance – work done by the Service Provider on a specific project Within 2 days | Service Provider Invoice Approval of TA Deliverable Approved Status Quo Report |
| Project Manager Project Director | Verify Invoice Verify that all the required documents are attached Verify that the work was done as per the agreed requirements and scope Request more information and/ or supporting documents if the above requirements are not met Recommend tax invoice payment and forward Papertrail to Project Director | Contract between Service Provider and Municipality New TA Guidance Notes Within 2 days per person | *link to TA payments Guidance Notes |
| Project Director | Recommend Approval Final recommendation of the requirements to approve the invoice. |  |  |
| Strategic Support Officer: Finance Specialist Finance Chief Director | Approve Invoice Verify that the tax invoice is valid as per S20(4) of the VAT Act Confirm the validity of the TCC Confirm that all payments to the Service Provider including the current one are within the Contractual Value Confirm that all payments to the Service provider including current one are within current year Gazette allocation Inform Project Administrator if any of the above is not met to request more information and/ or documents Check calculations of the invoice Recommend payment of tax invoice Approve tax invoice Forward tax invoice to Chief Director if outside Delegation. If not, sign as Chief Director and forward to relevant Proejcts administrator. Prepare invoice payment batch summary sheet | Schedule 7 Gazette allocation Sufficient remaining Schedule 7 Gazette allocation for the year Valid TCC Sufficient CV for the Service Provider Within 2 days | Final payments approval *link to delegation approval letter* *link to invoice payments batch summary sheet* *link to Schedule 7 Gazette allocations for the year* *link to the Schedule 7 remaining Gazette allocations for the year* *link to summary of TCC received* *link to summary of CV of Service Providers* *link to TA payments Guidance Notes* |
| Chief Director Specialist Finance | Pay Invoice Wet signatures on payment authorisation form Sign invoice payments batch summary sheet Scan and forward the batch to the financial service provider (Deloitte) Final release of tax invoice payments as per invoice payment batch summary sheet | Within 2 days Signed invoice payments batch summary sheet Original tax invoice and supporting documents | Final Payment Instruction (TA Payment) |

## Procedure Name: CG Draw Down

- Procedure Scope: CG Draw Down

Figure 62: Procedure Scope: CG Draw Down

Process Aim: To transfer schedule 6 funds to the primary bank account of municipalities to fund the construction of approved projects

- Procedure Model: CG Draw Down

Figure 63: Procedure Model: CG Draw Down

Table 30: CG Draw Down

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| NDP Finance Project Director | Verify Drawdown NP Finance generates the planned payment schedule for the applicable month. NDP Finance forwards the document to the project teams. Project Director approves/ rejects the planned CG draw down for the applicable month. Project Director provides reason for rejection. NDP Finance combines all inputs and presents combined view to CD CD approves the schedule with comments. | Due by 04’th of applicable month | Monthly Reports |
| Specialist Finance | Check Draw Down Financial Compliance Project Director compiles withholding letter for rejected drawdowns. Project Director gives hard copy of withholding letter to Specialist Finance Specialist Finance prepares an approved drawdown memo to Corp Services. Specialist Finance prepares a memo to IGR with the list of intended withholding and attach the withholding letters . | By 10 of every month. | Withholding templates. |
| Specialist Finance | Approve Drawdown Chief Director signs the hard copy of the memo to IGR and CFO and then signs the withholding letters. Chief Director gives originals to Specialist Finance. Specialist Finance forwards to project administrators who fax and email to the affected municipality. Copy of withholding letters to IGR with cover sheet of drawdowns for the month. Specialist Finance amends the payment schedule based on the withholding that took place Specialist Finance sends approved draw down (final payment instruction) to Corp Services for payment. | By 24’th of every month. Money released by 28’th of every month. By second day of following month | Final Payment Instruction (Capital Grant Transfers) |
| Corporate Service Specialist Finance | Reconcile BAS Corp Services transfers the funds to the municipalities. Corp Services sends updated BAS report to NDP Finance NDP Finance updates the MIS with successful payments. |  |  |

## Procedure Name: Retain Unspent Municipal Funds

- Procedure Scope: Retain Unspent Municipal Funds

Figure 64: Procedure Scope: Retain Unspent Municipal Funds

- Process Aim: To manage the rollover of unspent funds by the municipalities and the retention request that emanates to the IGR and to adjust the project and financial impact accordingly.

- Procedure Model: Retain Unspent Municipal Funds

Figure 65: Procedure Model: Retain Unspent Municipal Funds

Table 31: Retain Unspent Municipal Funds

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance Project Director | Request Municipal Roll Over Finance Specialist receives the retention deadlines from IGR – in line with Section 20 of the DoRA Finance Specialist communicates deadlines and workplan to Project Directors. Project Directors sends retention memo to all applicable municipalities (i.e. municipalities that had CG draw downs in the previous year) IGR sends retention request to all applicable municipalities. | Letter send to muni’s at the end of July Process driven by IGR, but NDP confirms process for its specific area. Due end August | Retention Request (example to be uploaded from I drive) Retention Letters (give hyperlink) |
| Specialist Finance | Review Municipal Roll Overs Municipal roll over (retention) requests uploaded by muni official onto the MIS Finance Specialist compiles an excel summary report of the requests. |  | Municipal Roll Over letters ADM300 > Supporting Documents > Financial Hyperlink to retention excel |
| Project Director Specialist Finance | Motivate Municipal Roll Overs Finance Specialist sends the document to the Project Directors who take note of the requests for future drawdowns and communicates any anomalies to the Finance Specialist / Chief Director | Standard rule: accepts all roll over requests |  |
| Specialist Finance | Submit Retention Request Finance Specialist compares the submissions to the NDP with the original requests received by the IGR department. Any anomalies are fed back to the Project Directors and followed up by them. Submits the NDP view / motivation report to IGR for consideration. | First week of Sept | Approved Retention Declined Retention |
| Specialist Finance | Update Final IGR decision Finance Specialist receives and uploads letters form IGR containing the approval / non approval of the retention request by the municipalities. Finance Specialist receives the final amounts to be offset by the IGR as part of the retention process Finance Specialist updates MIS with the returned funds as per the IGR letter. |  | ADM300 > Supporting Documents > Financial |

## Procedure Name: Submit Section 10 Reports

- Procedure Scope: Submit Section 10 Reports

Figure 66: Procedure Scope: Submit Section 10 Reports

- Process Aim: To report to IGR on the performance of the Grant regarding TA paid and CG transferred and spent by the municipality.

- Procedure Model: Submit Section 10 Reports

Figure 67: Procedure Model: Submit Section 10 Reports

Table 32: Submit Section 10 Reports

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Strategic Support Officer: Finance Project Administrator | Populate Section 10 DORA Report. Progress report on MIS closes for capturing by municipal officials Progress Report is verified by Project Teams – Project Director or Project Manager Finance Support pulls Summary Progress Report submissions from MIS Compare the amount of TA paid and CG transferred to the totals on the monthly reports Compare the monthly report data with the data submitted on the section 71 report. Confirm that the amount of CG actual spent YTD as per the progress report is not above CG transfers for the year. Limit the amount of CG actual spent to the amount of CG transferred for the year. Populate CG amount transferred, TA amount paid and the CG and TA amount actual spent on the NDPG6 - CG and NDPG7 - TA excel spread sheets (section 10 reports) from IGR Submit to specialist Finance for review | On the 17th of every month | Monthly Reports |
| Specialist Finance | Review Section 10 Report Verify that the total TA paid and CG transferred is as per the NDPG monthly reports Confirm that the amount of CG actual spent does not the CG transferred for the year Confirm overall accuracy of the report and address any anomalies on the report. Updates the summary section of the report. | On the 19th of every month | *link to the NDPG monthly report* |
| Specialist Finance | Submit Section 10 Report Email section 10 reports to IGR | On the 20th of every month | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.3 Financial & Management Info\6.3.19 Back up all years\20. Suzette\DORA reporting\201213 year\Sec 10 reports |

## Procedure Name: Generate Innovation Products

- Procedure Scope: Generate Innovation Products

Figure 68: Procedure Scope: Generate Innovation Products

- Process Aim

- Procedure Model: Generate Innovation Products

Figure 69: Procedure Model: Generate Innovation Products

Table 33: Generate Innovation Products

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Knowledge Management Specialist | Analyse Innovation Opportunities - Evaluate submissions - Prioritise submissions - Cluster submissions - Select potential projects | Criteria for evaluation, prioritisation and clustering: Optimise VFM, long term Impact, cross-sector & catalytic propensity & job creation Selection criteria: Internal resources Due date: October Frequency: A | Innovation Opportunities Proposed Innovation Portfolio |
| Knowledge Management Specialist | Determine Project Partnership / SP Requirement - Do stakeholder analysis per potential project - Undertake stakeholder reconnaissance - Generate roles and responsibilities matrix - Determine capacity requirements per potential project - Generate Terms of Reference per project and budget benchmarking | Stakeholder selection criteria: Willingness, credibility, technical know-how, purpose alignment SP criteria: specialisation, quantum, KPI impact, urgency Due date: March Frequency: A | Approved Innovation Portfolio Partnership Requirement Service / Provider Requirement |
| Knowledge Management Specialist | Package Innovation Products - Submit Partnership Agreement for Approval and signature by CD per project - Submit RFP for approval by CD - Recommend preferred SP - Manage partnership and SPs | Partnership Agreement: RFP: NT policy, clear and measurable outputs Recommend: VFM, experience, initiative Management of partners and SP: VFM, initiative Due date: December Frequency: Once-off | Innovation Projects |
| Knowledge Management Specialist | Submit Innovation Product - Presentation to NDP and partners - Prepare Innovation Product Report - Submit for approval | Optimise VFM, long term Impact, cross-sector & catalytic propensity & job creation Use NDP routing sheet for submission Due date: January Frequency: Once-off | Submitted Innovation Products – amend to “Innovation Product Report |
| Chief Director | Approve Innovation Product - Partners meeting - Approve | Optimise VFM, long term Impact, cross-sector & catalytic propensity & job creation Due date: February Frequency: Once-off | Approved Innovation Products Supported Innovation Product |

## Procedure Name: Mainstream Innovation Products

- Procedure Scope: Mainstream Innovation Products

Figure 70: Procedure Scope: Mainstream Innovation Products

- Process Aim

- Procedure Model: Mainstream Innovation Products

Figure 71: Procedure Model: Mainstream Innovation Products

Table 34: Mainstream Innovation Products

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Knowledge Management Specialist | e-Publish Innovation Product | NT Communications Department guidelines | Approved Innovation Products Proposed Mainstreaming Portfolio |
| Knowledge Management Specialist | Mainstream Approved Innovation Products |  | Mainstreamed Innovation Products Approved Mainstreaming Portfolio |
| Knowledge Management Specialist | Produce Innovation Product Material - Generate Terms of Reference per project and budget benchmarking | Price, quality, urgency | Service / Provider Requirement Innovation Product |
| Knowledge Management Specialist | Submit Proposed Mainstreaming Portfolio |  | Published Innovation Product |

# Authorisation

Approved / Not Approved

(D. Van Niekerk)

CHIEF DIRECTOR: NEIGHBORHOOD DEVELOPMENT PROGRAM

Date: