## Process Flow
1. DBSA
Division |  | Process Name | Document Number | Rev | Date
DBSA |  | DBSA PPF Panel Appointment
Process Interaction | NDP INTERACTION |  |  | Process Interaction
ANALYSIS SHEET
Timeframe
November
NT: MTEC Budget Workshops
Area for Improvement
To be loaded into MIS
Timeframe
November
NT: MTEC Budget Workshops
Area for Improvement
To be loaded into MIS
Timeframe
November
NT: MTEC Budget Workshops
Area for Improvement
To be loaded into MIS
PPF Panel Appointment process
Request to use PPF Resources
(Baseline Project Info)
MIS
PPF Administrator
Register the Request on PPF Database
1
PPF Database
Area for Improvement
PPF Database to to be developed
PPF Administrator
Allocate and notify PPF Co ordinator
1
PPF Coordinator
Conduct assessment and compile a TOR
(Input from Municipal Coordinator)
1
TOR
Municipal Coordinator
Sign off the TOR
1
TOR
PPF Coordinator
Procure PSP accourding to DBSA / PPF procurement
1
Letter of Appointment
PPF Coordinator & PSP
Sign the letter of appointmement
1
PPF Coordinator & PSP & Municipality Coordinator
Sign the SLA
1
SLA
(Signed)
PPF Coordinator
Compile the SLA
1
SLA
PPF Administrator
update PPF datyabase and upload SLA into MIS
1
MIS
PPF Panel Appointment process
PPF Database
Area for Improvement
Appointment timelines must be agreed
(4 weeks)

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
Finance |  | DBSA PPF Panel Appointment |  |  | 0% |  | 0 | 0 |  | 0 |  | 1 | 0 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recomendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | YES | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 1 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 9 | 8 | 0 | 0 | 0 | 1 | 0
[10 empty] | 0 | [10 empty] | 72

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0