National Treasury

Corporate Services

Chief Directorate: Neighbourhood Development Program

Financial Procedures

| Document No | NDP- |
| --- | --- |
| Version No |  |
| Owner | David Van Niekerk |
| Release Date |  |
| Document Classification |  |
| Compiled by | S Pretorius |

Glossary of Abbreviations

| Abbreviation | Description |
| --- | --- |
| BP | Business Plan |
| CD | Chief Director |
| IGR | Intergovernmental Relations |
| MIS | Management Information System |
| NDP | Neigborhood Development Programme |
| NT | National Treasury |
| PA | Project Administrator |
| PM | Project manager |
| PP | Project Plan |
| PD | Project Director |
| PDF | Portable Document Format |
| SLA | Service level Agreement |
| TOR | Terms of reference |
| TA | Technical Assistance |

Document Reference Library

| Document File Name | Context and Relevance |
| --- | --- |
| NDP Strategic Business Plan | Provide direction on future processes |
| NDP Annual Performance Plan | Provide direction on future processes |
| NDP Standard Operating Procedures | Provide information on existing processes |
| DOR Act | Provide compliance requirements |
| Neighborhood Development Partnership Grant | Provide compliance requirements |
| Applicable legislation / regulations | Provide compliance requirements |

Amendment History

| Version | Release Date | Description of Amendment | Amended By |
| --- | --- | --- | --- |
| 0 |  |  |  |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

TABLE OF CONTENTS

Introduction	6

Purpose	6

Document Scope	6

Business Process Decomposition	7

Identified Roles	9

Procedures	10

Procedure Name: Advertise the Grant	10

Procedure Name: Assess Municipal Applications	14

Procedure Name: Formalise the Funding Agreement	18

Procedure Name: Review Operational Guide for Municipalities	22

Procedure Name: Induct Municipal Officials	26

Procedure Name: Validate Service Provider	30

Procedure Name: Scope Programme	34

Procedure Name: Develop Programme Business Case	37

Procedure Name: Assess Portfolio	41

Procedure Name: Allocate Award	44

Procedure Name: Formalise the Funding Agreement	47

Procedure Name: Review Operational Guide for Municipalities	50

Procedure Name: Induct Municipal Officials	54

Procedure Name: Validate Service Provider	58

Procedure Name: Scope Programme	62

Procedure Name: Develop Programme Business Case	65

Procedure Name: Manage Precincts	68

Procedure Name: Review / Approve Project Plans	71

Procedure Name: Close Out Project	77

Procedure Name: Review BP / Programme	81

Procedure Name: Monthly Reporting	85

Procedure Name: Re-align Project Work Plans	89

Procedure Name: Segment Municipalities	93

Procedure Name: Municipal Performance Protocol	96

Procedure Name: Prioritise Pipelined Projects	99

Procedure Name: MTEF Budget	102

Procedure Name: In Year Budget	106

Procedure Name: DORA Payment Schedule	110

Procedure Name: TA Invoice Payment	114

Procedure Name: CG Draw Down	118

Procedure Name: Retain Unspent Municipal Funds	121

Procedure Name: Submit Section 10 Reports	125

Procedure Name: Generate Innovation Products	129

Procedure Name: Mainstream Innovation Products	133

Authorisation	136

TABLE OF FIGURES

Figure 1: NDP Business Processes (To Be)	7

Figure 2: Procedure Scopes	8

Figure 3: Example Diagram	9

Figure 4: NDP Core Business Roles	9

Figure 5: Procedure Scope: Advertise the Grant	10

Figure 6: Procedure Model: Advertise the Grant	11

Figure 7: Procedure Scope: Assess Municipal Applications	14

Figure 8: Procedure Model: Assess Municipal Applications	15

Figure 9: Procedure Scope: Formalise the Funding Agreement	18

Figure 10: Procedure Model: Formalise the Funding Agreement	19

Figure 11: Procedure Scope: Review Operational Guide for Municipalities	22

Figure 12: Procedure Model: Review Operational Guide for Municipalities	23

Figure 13: Procedure Scope: Induct Municipal Officials	26

Figure 14: Procedure Model: Induct Municipal Officials	27

Figure 15: Procedure Scope: Validate Service Provider	30

Figure 16: Procedure Scope: Scope Programme	34

Figure 17: Procedure Model: Scope Programme	35

Figure 18: Procedure Scope: Develop Programme Business Case	37

Figure 19: Procedure Model: Develop Programme Business Case	38

Figure 20: Procedure Scope: Assess Portfolio	41

Figure 21: Procedure Model: Assess Portfolio	42

Figure 22: Procedure Scope: Allocate Award	44

Figure 23: Procedure Model: Allocate Award	45

Figure 24: Procedure Scope: Formalise the Funding Agreement	47

Figure 25: Procedure Model: Formalise the Funding Agreement	48

Figure 26: Procedure Scope: Review Operational Guide for Municipalities	50

Figure 27: Procedure Model: Review Operational Guide for Municipalities	51

Figure 28: Procedure Scope: Induct Municipal Officials	54

Figure 29: Procedure Model: Induct Municipal Officials	55

Figure 30: Procedure Scope: Validate Service Provider	58

Figure 31: Procedure Model: Validate Service Provider	59

Figure 32: Procedure Scope: Scope Programme	62

Figure 33: Procedure Model: Scope Programme	63

Figure 34: Procedure Scope: Develop Programme Business Case	65

Figure 35: Procedure Model: Develop Programme Business Case	66

Figure 36: Procedure Scope: Manage Precincts	68

Figure 37: Procedure Model: Manage Precincts	69

Figure 38: Procedure Scope: Review / Approve Project Plans	71

Figure 39: Procedure Model: Review / Approve Project Plans	72

Figure 40: Procedure Scope: Close Out Project	77

Figure 41: Procedure Model: Close Out Project	78

Figure 42: Procedure Scope: Review BP / Programme	81

Figure 43: Procedure Model: Review BP / Programme	82

Figure 44: Procedure Scope: Monthly Reporting	85

Figure 45: Procedure Model: Monthly Reporting	86

Figure 46: Procedure Scope: Re-align Project Work Plans	89

Figure 47: Procedure Model: Re-align Project Work Plans	90

Figure 48: Procedure Scope: Segment Municipalities	93

Figure 49: Procedure Model: Segment Municipalities	94

Figure 50: Procedure Scope: Municipal Performance Protocol	96

Figure 51: Procedure Model: Municipal Performance Protocol	97

Figure 52: Procedure Scope: Prioritise Pipelined Projects	99

Figure 53: Procedure Model: Prioritise Pipelined Projects	100

Figure 54: Procedure Scope: MTEF Budget	102

Figure 55: Procedure Model: MTEF Budget	103

Figure 56: Procedure Scope: In Year Budget	106

Figure 57: Procedure Model: In Year Budget	107

Figure 58: Procedure Scope: DORA Payment Schedule	110

Figure 59: Procedure Model: DORA Payment Schedule	111

Figure 60: Procedure Scope: TA Invoice Payment	114

Figure 61: Procedure Model: TA Invoice Payment	115

Figure 62: Procedure Scope: CG Draw Down	118

Figure 63: Procedure Model: CG Draw Down	119

Figure 64: Procedure Scope: Retain Unspent Municipal Funds	121

Figure 65: Procedure Model: Retain Unspent Municipal Funds	122

Figure 66: Procedure Scope: Submit Section 10 Reports	125

Figure 67: Procedure Model: Submit Section 10 Reports	126

Figure 68: Procedure Scope: Generate Innovation Products	129

Figure 69: Procedure Model: Generate Innovation Products	130

Figure 70: Procedure Scope: Mainstream Innovation Products	133

Figure 71: Procedure Model: Mainstream Innovation Products	134

- TABLE OF TABLES

Table 1: Advertise the Grant	12

Table 2: Assess Municipal Applications	16

Table 3: Formalise the Funding Agreement	20

Table 4: Review Operational Guide for Municipalities	24

Table 5: Induct Municipal Officials	28

Table 6: Validate Service Provider	32

Table 7: Scope Programme	36

Table 8: Develop Programme Business Case	39

Table 9: Assess Portfolio	43

Table 10: Allocate Award	46

Table 11: Formalise the Funding Agreement	49

Table 12: Formalise the Funding Agreement	52

Table 13: Induct Municipal Officials	56

Table 14: Validate Service Provider	60

Table 15: Scope Programme	64

Table 16: Develop Programme Business Case	67

Table 17: Manage Precincts	70

Table 18: Review / Approve Project Plans	73

Table 19: Close Out Project	79

Table 20: Review BP / Programme	83

Table 21: Monthly Reporting	87

Table 22: Re-align Project Work Plans	91

Table 23: Segment Municipalities	95

Table 24: Municipal Performance Protocol	98

Table 25: Prioritise Pipelined Projects	101

Table 26: MTEF Budget	104

Table 27: In Year Budget	108

Table 28: DORA Payment Schedule	112

Table 29: TA Invoice Payment	116

Table 30: CG Draw Down	120

Table 31: Retain Unspent Municipal Funds	123

Table 32: Submit Section 10 Reports	127

Table 33: Generate Innovation Products	131

Table 34: Mainstream Innovation Products	135

# Introduction

- Operational procedures were identified during the development/review of the National Treasury PROCESS NAME Business Architecture. The operational procedures describe specific operational activities. The procedures serve several, if not all, of the following purposes:

  - It prescribes the events triggering the execution of the procedure.

  - It prescribes specific activities to be executed.

  - It prescribes specific responsibilities (specific roles related to specific activities).

  - It prescribes specific business rules guiding decision-making within the procedure.

  - It prescribes information flow between activities.

  - It prescribes which information items should be managed as quality records.

  - It prescribes the use of specific technology systems.

  - It prescribes the event ending the execution of the procedure.

## Purpose

- The aim of this document is to serve as formal record of documented operational procedures supporting the PROCESS NAME Business Architecture.

## Document Scope

- After the introductory part the document starts with a model representing an overview of NDP business processes and procedures. Each of the procedures that follows are described in the following order:

  - The first model creates a scope for the procedure followed by a model representing a flow of activities, information and responsibilities.

  - This process flow is followed by a more detailed description of the elements which form part of the procedure.

- Before the procedures are illustrated and described, the roles identified to support the identified procedures are illustrated. These roles are depicted as swim lanes within the process flow models.

# Business Process Decomposition

- The business process decomposition represents all the modelled work to be performed within the NDP organisation. This business process model was developed based on a relative clean slate approach where the objective was not to only incrementally improve existing business processes but to reconsider mission effectiveness and only thereafter process efficiency. On the highest level three generic process areas were proposed namely Unit Management, Core and Unit Support processes. Unit Management and Support processes were not further analysed as these are generic processes applicable to the entire NT. If the effectiveness / efficiency of these processes are to be questioned it should be directed to the relevant process owners within NT. The NDP is the process owner of only NDP core processes. These are the processes which are unique to the NDP mandate. Within the NDP Core business processes a business process owner was identified for each of the Core sub processes. These business process owners are ultimately responsible for the completeness, accuracy and currency of all Core business processes. Process owners are as follows:

  - Plan Programme A – Collins Sekele

  - Plan Programme B – David Van Niekerk / Collins Sekele

  - Manage Precincts – David Van Niekerk

  - Implement Programme – Irene Sinovich

  - Monitor Programme – Suzette Pretorius / Irene Sinovich

  - Grant Financial Management – Suzette Pretorius

  - Innovation and Mainstreaming – David Van Niekerk

Figure 1: NDP Business Processes (To Be)

- In order to interpret the two types of models used within every procedure consider the following guidelines:

  - All procedure scopes are represented by an activity model which can generically be illustrated as follows:

Figure 2: Procedure Scopes

  - Within these activity models the following definitions are applicable:

    - Activities represent real world functions. In a function model, activities are graphically shown as boxes and described by active verb phrases. Activities usually have concepts attached to them that describe what resources (controls, and mechanisms) the activity requires to produce the output or set of outputs. An activity must have at least one control attached to it for a method compliant diagram.

    - Inputs are resources consumed by or transformed by activities in the production of outputs. An input is represented by an arrow attached to the left side of an activity box.

    - An output is produced by an activity according to the resources (inputs, controls, and mechanisms) used by the activity. An output is represented by an arrow attached to the right side on an activity box.

    - A control is a resource, manufacturing guidelines for example, that constrains or guides an activity's production of outputs. A control is represented by an arrow attached to the top of an activity box.

    - Mechanisms are resources, such as employees or machines that are used by activities in producing an output. A mechanism is represented by an arrow attached to the bottom of an activity box.

  - More detail of each activity is captured in procedure models which can generically be illustrated as follows:

Figure 3: Example Diagram

# Identified Roles

- The following roles were identified as having specific responsibilities and to be accommodated within the core business structure of NDP. Quantities should be determined after work measurement / estimates and the application of applicable structuring principles.

Figure 4: NDP Core Business Roles

## Procedure Name: Prioritise Pipelined Projects

- Procedure Scope: Prioritise Pipelined Projects

Figure 5: Procedure Scope: Prioritise Pipelined Projects

- Process Aim: The purpose of this process is to have an overview of all submitted projects in the NDPG, whether approved or not approved as well as the stage that every project is in. This produces a pipeline (registry) of projects, prioritised according to certain criteria, that is used during different events of the NDP life cycle.

- Procedure Model: Prioritise Pipelined Projects

Figure 6: Procedure Model: Prioritise Pipelined Projects

Table 1: Prioritise Pipelined Projects

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance | Request updated cash flows from municipalities Specialist Finance request the project teams to ask for updated cash flows for their projects | 10 Sept – 10 Oct |  |
| Specialist Finance | Obtain Pipeline Report The Specialist Finance obtains a pipeline report from the MIS. | 15 October | Cash Flow Forecast Submitted NDP Projects |
|  | Review Pipeline Prioritisation This report is reviewed as follows: - By NDP Finance for accuracy and completeness of data - By the project portfolio’s for to agree with the prioritisation and or highlight any concerns - By the function that needs the report as input into a decision making process Pipeline criteria - Project status: Approved vs Not approved (submitted) - On-the ground ; tender phase ; approved ; - Urban / Rural - Municipal segmentation - Predicted Cash flow value | 16 – 30 October | Prioritised Pipelined Report |

## Procedure Name: MTEF Budget

- Procedure Scope: MTEF Budget

Figure 7: Procedure Scope: MTEF Budget

- Process Aim: The purpose of this process is to have the NDPG’s final 3 year budget figures confirmed with Corporate Services to finalise the municipal in-line allocations that needs to balance to these bottom line figures.

- Procedure Model: MTEF Budget

Figure 8: Procedure Model: MTEF Budget

Table 2: MTEF Budget

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Chief Director | Workshop Programme Forecast Chief Director attends the Programme Forecast and review meeting and presents information based on the strategy agreed in the NDP Strategic planning workshop held in February of every year. | May every year | None – presentation form CD with proposed/ indicative MTEF numbers |
| Chief Director | Workshop Annual Performance Review and Forecast Chief Director sets up the annual performance review and MTEF budget meeting This workshop - provides feedback and KPI review of the previous year - Discusses the situational / external environment changes that will impact the budget and operational procedures of the unit over the next 3 years - agrees the budgeting principles for the next MTEF period (starting the following year on 01 April) - highlights any gaps / concerns that needs to be addressed during the budget period over the next 3 months Reviews the pipelined projects in alignment with the above criteria and sets plan of action for aligning projects with budget plan. | Within the first week of July | MTEF Instruction(email from Corp Services) |
| Specialist Finance | Submit Adjusted Bottom Line Forecast for MTEF The Finance Specialist prepares the bottom line figures (1 for TA and 1 for CG) per year for the forthcoming MTEF / 3 year period. The Chief director reviews the allocation. If he is satisfied, he forwards the submission to Corporate Services. If not, he sends it back to the Finance Specialist for review. (In November, Corporate Services sends letters to all departments with their confirmed bottom line allocations for the MTEF periods as signed off by the CFO: NT) | This is usually due in the last week of July of every calendar year | Submitted MTEF Bottom Line Allocation Confirmed MTEF Bottom line Allocation |
| Specialist Finance | Evaluate MTEF Municipal Projections Specialist Finance pulls an updated pipeline report with the prioritised projects and derives cut off amount that aligns with the bottom line figures Specialist Finance forwards the portfolio allocations to the project directors for note and final comments Final comments received from PD’s and worked into final detail allocation proposal. | - 10 Nov | Confirmed MTEF Bottom Line Allocation (letter example on I drive) |
| Chief Director Specialist: Finance | Consolidate MTEF Municipal Projections Chief Director receives the Confirmed MTEF Allocation letter from Corporate services Letter is saved on i-drive by Business Support Manager and hard copy filed. CD informs Specialist Finance of the letter. Specialist Finance Reviews the values and notes any discrepancies from what was submitted. Finance submits to CD for final approval | 15 November | Confirmed MTEF Bottom Line Allocation (letter example on I drive) |
| Chief Director | Review MTEF Municipal Projections Specialist Finance prepares submission to IGR CD signs off final allocations | Allocations may only be rounded off to R’000 | MTEF Allocation Letter |
| Chief Director Specialist Finance | Submit Final Municipal MTEF Allocation Specialist Finance submits the MTEF allocation to Corporate Services and IGR. |  | Approved MTEF Budget |

## Procedure Name: In Year Budget

- Procedure Scope: In Year Budget

Figure 9: Procedure Scope: In Year Budget

- Process Aim: The purpose of this process is to have the NDPG’s final in- year budget figures confirmed with Corporate Services to finalise the municipal in-line allocations that needs to balance to this bottom line figure.

- Procedure Model: In Year Budget

Figure 10: Procedure Model: In Year Budget

Table 3: In Year Budget

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Chief Director | In Year Workshop Annual Performance Review and Forecast This workshop follows the ‘Workshop Annual Performance Review and Forecast’ and focuses on the In-Year budget specific. This meeting addresses the following: - Review of current projects on the ground - Review of pipeline projects - Any movements between TA and CG Risks and other measures to meet the budget. | Adjustments necessary for in year allocation | In Year Budget Instruction |
| Specialist Finance | Submit Adjusted Bottom Line Forecast for In Year Specialist Finance prepares adjusted in year allocations based on pipeline report and inputs from workshop Finance forwards the data to the CD: NDP to submit to Corporate Services | 1 – 8 Aug | Confirmed In Year Bottom Line Allocation |
| Specialist Finance | Evaluate In Year Municipal Projections Specialist Finance pulls an updated pipeline report with the prioritised projects and derives cut off amount that aligns with the bottom line figures Specialist Finance forwards the portfolio allocations to the project directors for note and final comments Final comments received from PD’s and worked into final detail allocation proposal. Intention to reduce allocation letters compiled by poroject teams and send to CD to sign. Letters sent to municipalities to inform them of the NDP’s intention to reduce their allocation. | 15 – 20 Oct 20 – 28 Oct 30 Oct 31 Oct | Adjusted Estimates for National Expenditure |
| Specialist Finance | Consolidate In Year Municipal Projections Appropriation Bill is tabled in Parliament Specialist Finance request confirmation of bottom line number from Corporate Services Specialist Finance Reviews the values and notes any discrepancies from what was submitted. | Last week October 5 working days after above |  |
| Specialist Finance | Review In Year Municipal Projections Specialist Finance prepares the in year allocation based on the prioritised pipeline report. This report is forwarded to the project teams to note and agree. Finance submits to CD for final approval |  |  |
| Chief Director Specialist Finance | Submit Final Municipal In Year Allocation Specialist Finance submits the final allocations to the Chief Director to sign off. Specialist Finance prepares the final submission of the in year allocation to Corporate Services and IGR. | Rounded to nearest R’000 | Approved In Year Budget Schedule 6&7 Gazette |

## Procedure Name: DORA Payment Schedule

- Procedure Scope: DORA Payment Schedule

Figure 11: Procedure Scope: DORA Payment Schedule

- Process Aim: This process aims to prepare the information to populate the payment schedule and Schedule 3A for the In Year.

- Procedure Model: DORA Payment Schedule

Figure 12: Procedure Model: DORA Payment Schedule

Table 4: DORA Payment Schedule

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance | Request Municipal Cash Flow Specialist Finance confirms the deadlines from IGR relating to the submission of the payment schedule to them (usually first week of May) Specialist Finance writes an email requesting the municipalities to confirm / submit their projected cash flows and forwards to the project teams. | As soon as the Dorbill is published (Mid-Feb) | Email |
| Project Administrator | Obtain Project Work Plan / Cash Flow Forward the email from Specialist Finance to the municipalities to confirm / submit their project cash flows on MIS for both TA(workplans) and CG)cash flows) for at least 18 months. Print the cash flow reports for each municipalities from MIS Ensure that all municipalities that has an allocation for TA and CG in the current year has submitted their cash flows Follow up on the municipalities that has not yet submitted their cash flows Submit all the cash flow reports from different municipalities to the Projects Manager | Due end March. Needs to balance with the gazetted allocation for the year. | Project Work Plan Submission Instruction Cash Flow Request |
| Project Director | Assess Project Work Plan / Cash Flow Assesses the cash flow report for each municipality Ensure the alignment of cash flows with current year allocation for both TA and CG Ensure the alignment of cash flows with approved projects Contact the municipality if further explanations are required Attends a meeting to discuss the cash flows with Specialist Finance and the Chief Director | 1 – 10 April | Cash flow reports from MIS |
| Chief Director | Approve Cash Flow Discuss the cash flows with Projects Director Approve the cash flows submitted by the municipalities Submit the Approved projected cash flows to Specialist Finance | 10 – 15 April | Summary of cash flow reports |
| Specialist Finance | Collate Drawdowns Ensure that the projected cash flows submitted are within the allocations for the year – final check Populate the payments schedule excel sheet received from IGR and send a copy to the project teams to sign off Submit the payments schedule to IGR by email | 16 – 30 April | Cash flow reports for all municipality |
| Specialist Finance | Obtain Signoff Schedule 3A's Confirms the publication of the payment schedule by NT on the NT website. Request Projects Administrator to inform muni’s | End May |  |

## Procedure Name: TA Invoice Payment

- Procedure Scope: TA Invoice Payment

Figure 13: Procedure Scope: TA Invoice Payment

- Process Aim – To reimburse the service providers on the work done for NDPG for Technical assistance.

- Procedure Model: TA Invoice Payment

Figure 14: Procedure Model: TA Invoice Payment

Table 5: TA Invoice Payment

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Team Assistant (NEO) | Receive Invoice Receive Service Provider tax invoice by a courier or hand delivered by the municipality or service provider. Acknowledge receipt of Service Provider tax invoice by way of a signature Date stamp all documents received from Service Provider Record all documents received on the NDPG receipt book Scan and save all documents received to the I-drive on the relevant project number Alert Project Administrator of tax invoice received | Must be original document. Day of receipt of tax invoice Same day | Service Provider Tax Invoice and supporting documents of work done and disbursements incurred Papertrail and hard copy in filing cabinet |
| Project Administrator | Prepare Invoice Upload and link the tax invoice and supporting documents to Papertrail on the relevant Municipality and project reference number Verify the validity of the claim according to the check list Request more information/ supporting documents if the above requirements are not met Recommend tax invoice payment to the Project Manager | Technical assistance – work done by the Service Provider on a specific project Within 2 days | Service Provider Invoice Approval of TA Deliverable Approved Status Quo Report |
| Project Manager Project Director | Verify Invoice Verify that all the required documents are attached Verify that the work was done as per the agreed requirements and scope Request more information and/ or supporting documents if the above requirements are not met Recommend tax invoice payment and forward Papertrail to Project Director | Contract between Service Provider and Municipality New TA Guidance Notes Within 2 days per person | *link to TA payments Guidance Notes |
| Project Director | Recommend Approval Final recommendation of the requirements to approve the invoice. |  |  |
| Strategic Support Officer: Finance Specialist Finance Chief Director | Approve Invoice Verify that the tax invoice is valid as per S20(4) of the VAT Act Confirm the validity of the TCC Confirm that all payments to the Service Provider including the current one are within the Contractual Value Confirm that all payments to the Service provider including current one are within current year Gazette allocation Inform Project Administrator if any of the above is not met to request more information and/ or documents Check calculations of the invoice Recommend payment of tax invoice Approve tax invoice Forward tax invoice to Chief Director if outside Delegation. If not, sign as Chief Director and forward to relevant Proejcts administrator. Prepare invoice payment batch summary sheet | Schedule 7 Gazette allocation Sufficient remaining Schedule 7 Gazette allocation for the year Valid TCC Sufficient CV for the Service Provider Within 2 days | Final payments approval *link to delegation approval letter* *link to invoice payments batch summary sheet* *link to Schedule 7 Gazette allocations for the year* *link to the Schedule 7 remaining Gazette allocations for the year* *link to summary of TCC received* *link to summary of CV of Service Providers* *link to TA payments Guidance Notes* |
| Chief Director Specialist Finance | Pay Invoice Wet signatures on payment authorisation form Sign invoice payments batch summary sheet Scan and forward the batch to the financial service provider (Deloitte) Final release of tax invoice payments as per invoice payment batch summary sheet | Within 2 days Signed invoice payments batch summary sheet Original tax invoice and supporting documents | Final Payment Instruction (TA Payment) |

## Procedure Name: CG Draw Down

- Procedure Scope: CG Draw Down

Figure 15: Procedure Scope: CG Draw Down

Process Aim: To transfer schedule 6 funds to the primary bank account of municipalities to fund the construction of approved projects

- Procedure Model: CG Draw Down

Figure 16: Procedure Model: CG Draw Down

Table 6: CG Draw Down

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| NDP Finance Project Director | Verify Drawdown NDP Finance generates the planned payment schedule for the applicable month. NDP Finance reviews the validity of the transfer @ business rules and make recommendation NDP Finance forwards the document to the implementation director. ID approves/ rejects the planned CG draw down for the applicable month. Project Director provides reason for rejection. NDP Finance combines all inputs and presents combined view to CD CD approves the schedule with comments. | Due by 04’th of applicable month Rules: - 80% spend @ transfers - Web report for past 2 months submitted | Monthly Reports |
| Specialist Finance | Check Draw Down Financial Compliance ID compiles withholding letter for rejected drawdowns. ID gives hard copy of withholding letter to Specialist Finance Specialist Finance prepares an approved drawdown memo to Corp Services. Specialist Finance prepares a memo to IGR with the list of intended withholding and attach the withholding letters . | By 10 of every month. | Withholding templates. |
| Specialist Finance | Approve Drawdown Chief Director signs the hard copy of the memo to IGR and CFO and then signs the withholding letters. Chief Director gives originals to Specialist Finance. Specialist Finance forwards to project administrators who fax and email to the affected municipality. Copy of withholding letters to IGR with cover sheet of drawdowns for the month. Specialist Finance amends the payment schedule based on the withholding that took place Specialist Finance sends approved draw down (final payment instruction) to Corp Services for payment. | By 24’th of every month. Money released by 28’th of every month. By second day of following month | Final Payment Instruction (Capital Grant Transfers) |
| Corporate Service Specialist Finance | Reconcile BAS Corp Services transfers the funds to the municipalities. Corp Services sends updated BAS report to NDP Finance NDP Finance updates the MIS with successful payments. |  |  |

## Procedure Name: Retain Unspent Municipal Funds

- Procedure Scope: Retain Unspent Municipal Funds

Figure 17: Procedure Scope: Retain Unspent Municipal Funds

- Process Aim: To manage the rollover of unspent funds by the municipalities and the retention request that emanates to the IGR and to adjust the project and financial impact accordingly.

- Procedure Model: Retain Unspent Municipal Funds

Figure 18: Procedure Model: Retain Unspent Municipal Funds

Table 7: Retain Unspent Municipal Funds

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Specialist Finance Project Director | Request Municipal Roll Over Finance Specialist receives the retention deadlines from IGR – in line with Section 20 of the DoRA Finance Specialist communicates deadlines and workplan to Project Directors. ID sends retention memo to all applicable municipalities (i.e. municipalities that had CG draw downs in the previous year) IGR sends retention request to all applicable municipalities. | Letter send to muni’s at the end of July Process driven by IGR, but NDP confirms process for its specific area. Due end August | Retention Request (example to be uploaded from I drive) Retention Letters (give hyperlink) |
| Specialist Finance | Review Municipal Roll Overs Municipal roll over (retention) requests uploaded by muni official onto the MIS Finance Specialist compiles an excel summary report of the requests. |  | Municipal Roll Over letters ADM300 > Supporting Documents > Financial Hyperlink to retention excel |
| Project Director Specialist Finance | Motivate Municipal Roll Overs Finance Specialist sends the document to the ID who take note of the requests for future drawdowns and communicates any anomalies to the Finance Specialist / Chief Director | Standard rule: rejects all roll over requests |  |
| Specialist Finance | Submit Retention Request Finance Specialist compares the submissions to the NDP with the original requests received by the IGR department. Any anomalies are fed back to the Project Directors and followed up by them. Submits the NDP view / motivation report to IGR for consideration. | First week of Sept | Approved Retention Declined Retention |
| Specialist Finance | Update Final IGR decision Finance Specialist receives and uploads letters form IGR containing the approval / non approval of the retention request by the municipalities. Finance Specialist receives the final amounts to be offset by the IGR as part of the retention process Finance Specialist updates MIS with the returned funds as per the IGR letter. |  | ADM300 > Supporting Documents > Financial |

## Procedure Name: Submit Section 10 Reports

- Procedure Scope: Submit Section 10 Reports

Figure 19: Procedure Scope: Submit Section 10 Reports

- Process Aim: To report to IGR on the performance of the Grant regarding TA paid and CG transferred and spent by the municipality.

- Procedure Model: Submit Section 10 Reports

Figure 20: Procedure Model: Submit Section 10 Reports

Table 8: Submit Section 10 Reports

| Responsibility | Activity Description | Decision Rules | Supporting systems / Quality records (QRs) |
| --- | --- | --- | --- |
| Strategic Support Officer: Finance Project Administrator | Populate Section 10 DORA Report. Progress report on MIS closes for capturing by municipal officials Progress Report is verified by Project Teams – ID or Project Manager Finance Support pulls Summary Progress Report submissions from MIS Compare the amount of TA paid and CG transferred to the totals on the monthly reports Compare the monthly report data with the data submitted on the section 71 report. Confirm that the amount of CG actual spent YTD as per the progress report is not above CG transfers for the year. Limit the amount of CG actual spent to the amount of CG transferred for the year. Populate CG amount transferred, TA amount paid and the CG and TA amount actual spent on the NDPG6 - CG and NDPG7 - TA excel spread sheets (section 10 reports) from IGR Submit to specialist Finance for review | On the 17th of every month | Monthly Reports |
| Specialist Finance | Review Section 10 Report Verify that the total TA paid and CG transferred is as per the NDPG monthly reports Confirm that the amount of CG actual spent does not the CG transferred for the year Confirm overall accuracy of the report and address any anomalies on the report. Updates the summary section of the report. | On the 19th of every month | *link to the NDPG monthly report* |
| Specialist Finance | Submit Section 10 Report Email section 10 reports to IGR | On the 20th of every month | I:\BR_Budget Office\4.CD_NDPG\1 NDP Unit\6.3 Financial & Management Info\6.3.19 Back up all years\20. Suzette\DORA reporting\201213 year\Sec 10 reports |