## MEETING SHEDULE NOT (hidden)
(AS IS) - PROCESS MAP REVIEW AND AUDIT NOTIFICATION
(AS IS) - PROCESS MAP REVIEW AND AUDIT NOTIFICATION - REV - A
DATE SENT: | 2013-10-29 |  |  | NOTE: PLEASE CONFIRM VIA EMAIL PROJECT LEAD: DAVE REEVELL dave@bip.co.za PROJECT MANAGER: CHAD REEVELL creevell@gmail.com
DATE REQUESTED: | 2013-11-06
REQUESTED BY: | C.REEVELL
DEPARTMENT: | STAKE HOLDER RELATIONSHIP / RESEARCH & SKILLS PLANNING
AGENDA
ACTION: | START TIME: | TIME END:
KICK OFF MEETING: | 8:00 | 8:15 | STAKE HOLDER RELATIONSHIP |  | MORNING
PROCESS MAPS REVIEW: | 8:15 | 9:00 | RESEARCH & SKILLS PLANNING |  | AFTERNOON
PROCESS AUDIT: | 9:00 | 16:45
AUDIT FEEDBACK: | 16:45 | 17:00

## OVERALL CHARTS
PROCESS DEFECT & IMPACT ANALYSES
OVERALL |  | NUMBER ISSUES TO BE ADDRESSED | 47 | TOTAL NUMBER OF IMPACT'S | 69
CONDUCTED ON:
CONDUCTED BY: | [6 empty] | Programme Mgt | Corp Support | Knowl and Comm |  |  |  |  | TOTAL
[6 empty] | DOCUMENTATION | 24 | 1 | 0 | 0 | 0 | 0 | 0 | 25
[6 empty] | SYSTEM | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
[6 empty] | RESOURCES | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
[6 empty] | PROCESS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
TOTAL
[6 empty] | Within the Dept | Programme Mgt | Corp Support | Knowl and Comm |  |  |  |  | 0
[6 empty] | By another Dept | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | External to NDP | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7
TOTAL
[6 empty] | PERFORMANCE | Programme Mgt | Corp Support | Knowl and Comm |  |  |  |  | 0
[6 empty] | TIME DELAY | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13
[6 empty] | ACCURACY | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17
[6 empty] | COMPLIANCE | 38 | 1 | 0 | 0 | 0 | 0 | 0 | 39
TOTAL
[6 empty] | Low | Programme Mgt | Corp Support | Knowl and Comm |  |  |  |  | 0
[6 empty] | Medium | 50 | 2 | 0 | 0 | 0 | 0 | 0 | 52
[6 empty] | High | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50

## Programmes
PROCESS DEFECT & IMPACT ANALYSES
Phase |  | Programme Initiation
[18 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
[18 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[6 empty] | IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 12 | Within the Dept | 39 | Performance | 34 | Low | 2
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 24 | By another Dept | 0 | Time Delay | 13 | Medium | 50
| Non Metro - Programme Initiation Phase 1 | [8 empty] | System | 5 | External to NDP | 7 | Accuracy | 17 | High | 50
1 | Using evaluation criteria drive the needs analysis of Municipality needs. What format, tools to engage with the municipality. The input into the process is a list of Municipalities that the NDP want to engage with. |  |  | Documentation | Within the Dept | Medium |  |  | Medium | Resources | 5 |  |  | Compliance | 38
2 | Currently mapping on proposed new structure, therefor it needs to be approved |  |  | Resources | Within the Dept | Medium |  |  | High
3 | Project planning tool held with Planning Director. This needs to be checked |  |  | Documentation | Within the Dept | High | Medium |  | Medium
4 | We need to clarify who we engage with in the Municipality ( to what level do we communicate with ). The NDP team currently requests the municipality to nominate a person. There is a Municipality contact database with contact details that is used. How do we keep this current. Lessons learnt from problem municipalities. |  |  | Resources | External to NDP | Medium | High |  | Medium
5 | Standard for contact letter and email needs to be developed |  |  | Documentation | Within the Dept | Medium |  | Medium | Low
6 | Does the CD need to review and sign off all communication. If so, what and when. What delegation of authority and responsibility is in place. |  |  | Process | Within the Dept | High |  |  | High
7 | Project / engagement numbering system needs to be agreed. |  |  | Documentation | Within the Dept |  |  | Medium | Medium
8 | We need to specify and document what format of communication is required and when ( email, letter ) |  |  | Process | Within the Dept | Medium |  | Medium | High
9 | New filing structure needs to be tabled with Revworth team for inclusion into processes |  |  | Documentation | Within the Dept | Medium |  | High
10 | When we engage with the Municipality / Metro, we need to check and update the Municipality Contact List in point 5. |  |  | Documentation | Within the Dept |  | Medium | Medium
11 | Look at developing "Toolkit" approach on capacitating the municipality on the Work Plan development, etc. |  |  | Documentation | Within the Dept | High |  |  | Medium
12 | Need to look at having the Work Plan completed "online" by the municipality as well as who is responsible to drive the review within the NDP. Will the NDP sign the Work Plan or use a Letter of Acceptance as a cover to the Work plan |  |  | System | Within the Dept | High |  | High | High
13 | The filing structure and naming needs to be reviewed and agreed. Example - during the Programme Initiation Phase we do not have a Project File ( maybe a Programme or Engagement file ) |  |  | Documentation | Within the Dept |  |  | Medium | Medium
14 | How the NDP formally receives and issues information and documents needs to be identified, formalised and implemented. |  |  | Process | Within the Dept | Medium |  |  | High
15 | Where is it identified and agreed who appoints the Service Provider at 1.5. |  |  | Documentation | Within the Dept | Medium | High |  | Medium
16 | NDP needs to provide Service Provider criteria selection guidelines for the Municipality to appoint the correct service provider |  |  | Resources | External to NDP | High
17 | Resource planning needs to be looked at with regards to available resources, logistics, etc. Example - briefing session with TA Consultant |  |  | Resources | Within the Dept | Medium | Medium
18 | Consultant Pack at TA Consultant needs to be updated with "Lessons Learnt" |  |  | Documentation | Within the Dept | Medium
19 | The Project File name could be named according to phase. Example - TA Project File |  |  | Documentation | Within the Dept |  |  | Medium
20 | Delegation of authority and approvals to changes to Work Plan and Costing needs to be agreed. |  |  | Documentation | Within the Dept | Medium |  |  | High
Non Metro - Network Planning Phase 2
21 | When the Municipality populates the NDP templates using the NDP guidelines, would there be additional support / training required ( Toolkit ) |  |  | Documentation | Within the Dept | Medium | Medium | High | High
22 | Can all the templates and communication be done 'online" |  |  | System | External to NDP | High | High | High | High
23 | Fast tracking of Precinct planning happens prior to Letters of Approval |  |  | Process | Within the Dept |  |  |  | High
Non Metro -Precinct Planning Phase 3
24 | Look at Urban Design Toolkit to see if we can include further improvements ( are there any "lessons learnt" as yet ) |  |  | Documentation | Within the Dept | Medium |  |  | Medium
25 | 3.1 The name Precinct Design Plan covers both Precinct as well as Sub Precinct design planning. Business rules / guidelines need to be developed around this |  |  | Process | Within the Dept | Medium |  |  | Medium
26 | Is the Status Quo Report emailed or can it be uploaded into the MIS. Possibility of email and then save on I:/drive server |  |  | System | External to NDP | Medium | Medium
27 | We need a compliance checklist / criteria for 3.1.1 (1) when the NDP Project manager and team review the status quo report. The NDP needs to email back that NOTED of Status Quo Report receipt and review |  |  | Documentation | Within the Dept | Medium |  | Medium | Medium
28 | As part of the development of 3.1.2 there are various interactions between the NDP Project Manager / team and the municipality. These sessions should be minuted and filed on the I:/drive |  |  | Documentation | External to NDP | Medium |  |  | Medium
29 | Technical review of Draft Precinct Design Plan needs a checklist that is used as part of the review |  |  | Documentation | Within the Dept | High |  | High | High
30 | Task team of specialists review of the Draft Precinct Design Plan needs a checklist / evaluation rating that is used as part of the review |  |  | Documentation | Within the Dept | High |  | High | High
31 | Need to repeat 29 and 30 for Final submissions as well |  |  | Documentation | Within the Dept | High |  | High | High
32 | Does the CD need to sign the Acceptance Letter at 3.1.4 (1). |  |  | Process | Within the Dept |  |  | Medium | Medium
33 | 3.2 Terminology of "Feasibility Study" in 3.2.2 needs to be defined and understood supported by an example of how it reduces risk and increases understanding. Parameters and guidelines need to be developed. The Toolkit has guidelines on the precinct phasing approach / steps ( review them to see what detail has been documented ) 3.2.3 - first 3.2.2 - second 3.2.1 - third within phase 3.2 |  |  | Documentation | Within the Dept |  |  |  | High
34 | 3.3 The word "Concept" ( Town Planning Scheme ) needs to be understood 3.3 |  |  | Process | Within the Dept |  |  |  | Low
35 | In 4.1, the wording "Precinct" needs to be renamed "Project Plan" as we can not change commercial aspects at this stage, only sequence with input form Planning |  |  | Process | Within the Dept |  |  |  | Medium
36 | Acceptance could be done directly on MIS ( at activity 24 of 3.2 ) |  |  | System | Within the Dept | Medium |  |  | Medium
Non Metro -Implementation Phase 4
25 | The procurement of the CG Consultant ( can take 3 months ) should start in the planning phase. Maybe start after 3.2 - as input into 3.3 Precinct Concept Planning ( maybe one consultant for one precinct ). Appointment should be at 4.1. |  |  | Resources | External to NDP |  | Medium
26 | Changes to Precinct Concept Plan after review by PM: PD and ID needs to go through proper change control management. ( this should apply to any changes at any phase ) |  |  | Process | Within the Dept |  | Medium |  | High
27 | The wording "Project Plan" needs to be defined within the NDP structure. What constitutes the input into the Project Plan needs to be defined. |  |  | Process | Within the Dept |  |  |  | High
28 | The output of the Feasibility and Prelim Design by MCO " Project Concept Baseline" ( was called Project Plan by NDP ) is submitted to the NDP. The " Project Concept Baseline" requires a template to be designed |  |  | Documentation | Within the Dept | High |  | High | High
29 | What gets loaded into the MIS and what needs to be submitted in hard copy needs to be agreed and documented |  |  | Process | External to NDP | High | Medium |  | High
30 | Deliverables during Construction Phase needs to be documented that would release payments, etc ( do they upload the MIS every 3 months ) |  |  | Documentation | Within the Dept | Medium | Medium |  | High
31 | Site visits are done by 30% and 90% payment release. This needs to be built into the MIS to ensure that the site visits have been done |  |  | System | Within the Dept | High |  |  | High
32 | Final Construction Close Out deliverables need to be defined as well as how the NDP verifies them and what is updated. Site Visit should be built in. ( example - practical completion test ) |  |  | Documentation | Within the Dept | High |  |  | High
33 | What the Final Project Close out deliverables need to be defined as well as how the NDP verifies them and what is updated. |  |  | Documentation | Within the Dept | High |  |  | High
34 | Project Close-out needs "lessons learnt" included as well as key success areas ( example - Jobs created, savings, etc. ) |  |  | Process | Within the Dept | High | High | High | High

## Finance
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT: |  | Finance
[18 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
[18 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[6 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 1 | Performance | 1 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 1 | By another Dept | 0 | Time Delay | 0 | Medium | 2
| 1.1 Engage with Client | [8 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
| MOA ( Financial Inputs ) - Indicative envelope for technical assistance and capital grant. CD to clarify if NDP to follow this process |  |  | Documentation | Within the Dept | Medium |  |  | Medium | Resources | 0 |  |  | Compliance | 1
1.2 Establish Work Plan
Municipal Co-ordinator - Draft Work Plan: How the NDP Finance review the required budget needs to be addressed and formalised
Work Plan to be submitted in MIS using form in MIS ( currently using Outlook with attached file )
Can notification of approvals back to Municipality be done through MIS .

## 3
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT:
[17 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
[17 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[5 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 0 | Performance | 0 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 0 | By another Dept | 0 | Time Delay | 0 | Medium | 0
[9 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
[9 empty] | Resources | 0 |  |  | Compliance | 0

## 4
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT:
Process | [16 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
Process Owner | [16 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[5 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 0 | Performance | 0 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 0 | By another Dept | 0 | Time Delay | 0 | Medium | 0
[9 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
[9 empty] | Resources | 0 |  |  | Compliance | 0

## 5
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT:
Process | [16 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
Process Owner | [16 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[5 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 0 | Performance | 0 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 0 | By another Dept | 0 | Time Delay | 0 | Medium | 0
[9 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
[9 empty] | Resources | 0 |  |  | Compliance | 0

## 6
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT:
Process | [16 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
Process Owner | [16 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[5 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 0 | Performance | 0 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 0 | By another Dept | 0 | Time Delay | 0 | Medium | 0
1 | [8 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
2 | [8 empty] | Resources | 0 |  |  | Compliance | 0
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32

## 7
PROCESS DEFECT & IMPACT ANALYSES
DEPARTMENT: |  | INTERNAL AUDIT
Process | [17 empty] | CONSTRAINT TYPE |  | WHERE |  | IMPACT |  | LEVEL
Process Owner | [17 empty] | DOCUMENTATION | 0 | DEPT. INTERNAL | 0 | PERFORMANCE | 0 | HIGH | 0
[6 empty] | DEFECT IMPACT ON YOUR DEPARTMENT |  |  |  | Process | 0 | Within the Dept | 0 | Performance | 0 | Low | 0
CON # | CONSTRAINT DESCRIPTION FROM PROCESS MAP WORKSHOP |  |  | DEFECT TYPE | CREATED BY | PERFORMANCE | TIME DELAY | ACCURACY | COMPLIANCE | Documentation | 0 | By another Dept | 0 | Time Delay | 0 | Medium | 0
[10 empty] | System | 0 | External to CRAN | 0 | Accuracy | 0 | High | 0
[10 empty] | Resources | 0 |  |  | Compliance | 0