## Process Flow
5 Implementation
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 5.1 Inception Stage 1 | NDP – IM – 03 - 001 | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
Review Precinct Concept Plans
Input
- Precinct Concept Plans
- Table of Prioritised Projects
- Appointment CGC (Letter)
Municipal Co-ordinator and Professional Service Provider (PSP)
Start with Procurement process
1
MIS
Professional Service Provider (CG)
Establish Scope of Work and Preliminary Project Execution Plan (or Project Brief )
ASSUMPTION : CG (PSP) Consultant appointed prior to 4.1
5
Municipal Co-ordinator Check plan against Precinct Concept Plan
6
O.K.
Yes
No
MIS
Project Manager, Project Implementation Director
Receive Preliminary Project Execution Plan and Review. Comments sent to Municipal Co-ordinator and PSP
7
Preliminary Project Execution Plan
Preliminary Project Execution Plan with comments
Municipal Co-ordinator and / or Professional Service Provider (CG)
Update as per comments and submit
8
File
I Drive File
Updated Preliminary Project Execution Plan with comments
MIS
5.2 Concept Viability Stage 2 (Preliminary Design)
Project Manager, Project Implementation Director
Receive updated Preliminary Project Execution Plan
9
Budget Input CG
COMPLETED PRECINCT PLAN
Area For Improvement
provide template to municipal coordinator to speed-up the review process
Area For Improvement
Information and documentation can be issued and approved on MIS
3.3 Listing and Prioritising of NDP Projects
Municipal Co-ordinator
Add municipal information and start procurement
2
Procurement / Tender Process
Appointed TA Consultant(s)
Municipal Co-ordinator
Issue a Service Level Agreement
3
Service Level
Agreement
1.5.2 (2)
Letter of
Appointment
1.5.2 (1)
Project Manager Schedule a Briefing Session with the Consultant
4
MIS
Procurement Option
MIS
NDP panel resources
(DBSA)
MIS
Project Portfolio Management process
Permission To proceed
MIS

## AUDIT CRITERIA
[22 empty] | SCORE |  |  |  |  | IMPACT ON RISK | CRITICALITY | ACTION | KPI DATA SOURCE
[21 empty] | NA | Not Applicable |  |  |  |  | YES | LOW | OPEN | YES
Division |  | Process Name |  | OVERALL COMPLIANCE |  |  | RAISED ACTIONS | OPEN ACTIONS |  | CLOSED ACTIONS |  | RISK IMPACTS | KPI DATA SOURCE POINTS | [7 empty] | 0 | PROCESS NOT FOLLOWED / NO EVIDENCE COULD BE PROVIDED |  |  |  |  | NO | MEDIUM | CLOSED | NO
PROGRAMME MANAGEMENT |  | 4.1 Inception Stage 1 |  |  | 0% |  | 0 | 0 |  | 0 |  | 1 | 1 | [7 empty] | 1 | PROCESS FOLLOWED BUT EVIDENCE DID NOT MEET THE REQUIREMENTS |  |  |  |  | NOT SURE | HIGH
AUDIT CRITERIA | [20 empty] | 2 | PROCESS FOLLOWED BUT IMPROVEMENTS REQUIRED
[21 empty] | 3 | MEETS REQUIREMENTS
AUDIT QUESTION |  | EVIDENCE REQUIRED | EVIDENCE PROVIDED |  |  | FINDING |  |  |  | SCORE | CRITICALITY | RECOMMENDATIONS | ACTIONED BY WHO | ACTIONED BY WHEN (Date / Month / Year ) | ACTIONED OPEN / CLOSED | IMPACT ON RISK | RISK DESCRIPTION | KPI DATA SOURCE | KPI DATA SOURCE INDICATION | TIME AND VOLUME | possible score | X criticality | Recommendations | Action Open | Action Closed | Impact on Risk | KPI data source
1 | Project related documentation filed and easy to trace | Project Files ( both hard copy and electronic ) | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | Auditee can find the respective process map contained in the NDP PORTAL | Auditee can source the respective process maps on the NDP Portal | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
3 | Has there been any Change Requests / Variation Orders been raised. | Is the status on the systems been updated and reflect the current status | [8 empty] | HIGH |  |  |  |  | NOT SURE | Budget Impact with regards to spend and other project impacts |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
4 | Has the PM received the Terms of Reference and Appointment Letter from the Municipality Co-ordinator and/or NDP Panel (DBSA). | Filed ToR and Appointment Letter | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
5 | Has the MIS been updated with current project status | MIS updated | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
6 | Has the PM chaired the Briefing Session with the Consultant | Service Level Agreement Letter of Appointment Minutes | [8 empty] | MEDIUM | [9 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0
7 | Has the Professional Service Provider (PSP) submitted the "Preliminary Project Execution Plan" for review by the PM | Reviewed "Preliminary Project Execution Plan" on file | [8 empty] | HIGH | [9 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0
8 | Has any changes to the "Preliminary Project Execution Plan" been formally communicated to the PSP and changes received. | Formal request issued to PSP ( email / MIS ) | [8 empty] | HIGH |  |  |  |  | YES | Accepted "Project Execution Plan" accepted against set criteria | YES | No of approved projects in implementation (as % of gazette) |  | 3 | 3 | 0 | 0 | 0 | 1 | 1
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL | 0 | [10 empty] | 24 | 21 | 0 | 0 | 0 | 1 | 1
[10 empty] | 0 | [10 empty] | 504

## KPI DATA SOURCE
KPI DATA SOURCE
| Data/KPI | Total number of executive engagements completed | Total number of approved / revised Urban Networks | Total number of approved Precinct Plans (Urban Hubs) | No of approved projects in implementation (as % of gazette) | Total number of Precincts (Urban Hubs) operational | Total number of Partnerships concluded | Financial Leverage
1 | Province | X | X | X | X | X | X | X
2 | Municipality Name | X | X | X | X | X | X | X
3 | Municpal Code | X | X | X | X | X | X | X
4 | Municipal NDPG Coordinator Details | X | X | X | X | X | X | X
5 | Municipal CSP Coordinator Details | X | X | X | X | X | X | X
6 | PPF Coordinator Details | X | X | X | X | X | X | X
7 | NDP Projects Manager | X | X | X | X | X | X | X
8 | Municipal Location | X | X | X | X | X | X | X
9 | Municipal Envelope |  |  | X | X | X | X | X
10 | Municipal Gazette |  |  | X | X | X | X | X
11 | Municipal Payment Schedule |  |  | X | X | X | X | X
12 | PPF Allocation |  |  | X | X | X | X | X
13 | Network Description | X | X | X | X | X | X | X
14 | CBD Location | X | X | X | X | X | X | X
15 | Integration Zone Name | X | X | X | X | X | X | X
16 | Integration Zone Code | X | X | X | X | X | X | X
17 | Primary Network Modal Classification | X | X | X | X | X | X | X
18 | Development Corridor (?) | X | X | X | X | X | X | X
19 | Council Resolution Date |  | X | X | X | X | X | X
20 | Integration Zone Priority |  | X | X | X | X | X | X
21 | Township Cluster Description | X |  | X | X | X | X | X
22 | Township Cluster Location | X |  | X | X | X | X | X
23 | Township Cluster Population | X |  | X | X | X | X | X
24 | Urban Hub Name | X |  | X | X | X | X | X
25 | Urban Hub Code | X |  | X | X | X | X | X
26 | Urban Hub Location | X |  | X | X | X | X | X
27 | Urban Hub Distance to CBD | X |  | X | X | X | X | X
28 | Precinct Stakeholders |  |  | X |  | X | X | X
29 | Precinct Work Plan |  |  | X
30 | Precicnt Plan Professional Team Details |  |  | X
31 | Precinct Plan Duration |  |  | X
32 | Precinct Plan Cost |  |  | X
33 | Precinct Plan Status |  |  | X | X
34 | Urban hub Sub-Precinct Name |  |  | X | X
35 | Precinct Table of Project Description |  |  | X | X
36 | Precinct Table of Project Locations |  |  | X | X
37 | Precicnt Plan Acceptance Date |  |  | X | X
38 | Precinct Management Work Plan |  |  |  |  | X
39 | Precicnt Management Professional Team Details |  |  |  |  | X
40 | Precinct Management Plan Duration |  |  |  |  | X
41 | Precinct Management Plan Cost |  |  |  |  | X
42 | Precinct Plan Management Plan Status |  |  |  |  | X
43 | Precicnt Management Plan Submitted |  |  |  |  | X
44 | Precinct management Plan Approved |  |  |  |  | X
45 | Urban Hub Leverage | [6 empty] | X
46 | Registered Project Type |  |  |  | X
47 | Registered Project Code |  |  |  | X
48 | Registered Project Category |  |  |  | X
49 | Registered Project Location |  |  |  | X
50 | Project Cashflow |  |  |  | X
51 | Project Procurement Route |  |  |  | X
52 | Project Professional Fees |  |  |  | X
53 | Project Cost of Works Submitted |  |  |  | X
54 | Project Cost of Works Benchmarked |  |  |  | X
55 | PPIP Value (Baseline 0) |  |  |  | X
56 | PPIP Approval Date |  |  |  | X
57 | Professional Team Details |  |  |  | X
58 | PPC Value (Baseline 1) |  |  |  | X
59 | PPC Approval Date |  |  |  | X
60 | Project Tender Value (Baseline 2) |  |  |  | X
61 | Project Stage |  |  |  | X
62 | Project Status |  |  |  | X
63 | Project Spend |  |  |  | X
64 | Project Construction Value (Baseline 3) |  |  |  | X
65 | Close Out Value |  |  |  | X |  |  | X
66 | Close Out Date |  |  |  | X |  |  | X

## NDP STAFF LIST
Senior Management Team
Chief Director
Project Director
Project Manager
Strategy Specialist
Technical Adviser Consultant
Financial Director
Financial Specialist
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
0
0
0
0
0
0
0