## Process Flow
5 Implementation
Division |  | Process Name | Document Number | Rev | Date
Urban Design - Non Metro |  | 5.4 Documentation and Procurement Stage 4 (Tender) |  | 0 | 2014-01-29
Municipal Interaction | NDP INTERACTION |  |  | Municipal Interaction
5.3
Design Development Stage 3
(Detail Design)
Project tender baseline
MIS
Municipal Co-ordinator and Profesional Service Provider (PSP)
Implement the tender process: Preparation of tender docs, Tender issuance and tender evaluation
4
Municipal Co-ordinator and Profesional Service Provider (PSP)
Appoint contractors
7
Project Construction Baseline
Project Manager
Check and capture into MIS
8
MIS
Project Construction Baseline
5.5
Contract Administration & inspection
Stage 5 (Construction)
Project Construction Baseline
File
I Drive File
Includes :
- Tender Documents
- Construction Award
- Baseline 3
- Costing
- Cash Flow
- Bill of Quantities update
Proceed with Appointment (>10% Variance)
Yes
No
Area For Improvement
Proceed rules to be determined and included
Area For Improvement
Update project portfolio on MIS.
Will it be possible for MIS to automatically update the project portfolio on the upload of the project concept baseline.
Project Manager
Notify the Municipal co coordinator to arrange additional funding as per MOU
5
Municipal Co-ordinator and Profesional Service Provider (PSP)
Submit for council approval
6
Notification
Council Approval
Yes
No
Process to be defined
and agreed
NDP Monitoring process
Permission to Proceed with Construction
MIS
MIS
Portfolio Management
MIS
Project Manager
Submit for approval of cost of works
1
Permission to Proceed with Construction
Project Implementation Director
Review and Recommend for approval
2
Chief Director
Review and Approve
3
MIS

## High Level Table
PROGRAMME MANAGEMENT (HIGH-LEVEL PROCESS AND BENEFITS REALISATION)
Management Approach: Urban Network and Precinct Development (Phases, Milestones, Gates, Baselines, Deliverables, Reviews, Audits)
PHASE | 1 Programme Initiation |  |  |  |  | 2 Network Planning |  | 3 Precinct Planning |  |  | 4 Implementation
| 1A | 1B | 1C | 1D | 1E | 2A | 2B | 3A | 3B | 3C | 4A | 4B | 4C | 4D | 4E | 4F
| 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 2.1 | 2.2 | 3.1 | 3.2 | 3.3 | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6
SUBPHASE | Engage with the Client | Establish Work Plan | Identify Urban Network Elements | Conclude Contrcatual Arrangements | Appoint TA Consultant(s) , final Work Plan and Funds | Conduct Urban Network Phasing | UN Order Costing | Conduct Precinct Planning | Conduct Precinct Concept Planning | Listing and Prioritising of NDP Projects | Inception Stage | Feasibility / Preliminary Design ( Concept & Viability ) | Detail Design ( Design Development ) | Tender ( Documentation and Procurement ) | Construction ( Contract Administration and Inspection ) | Close-out
MILESTONE |  |  | 1 | 2 |  |  | 3 | 4 | 5 | 6 |  |  | 7 | 8 | 9 | 10
GATES | 1.3: 1; 1.4: 2; 2.2: 3; 3.1: 4; 3.2: 5; 3.3: 6; 4.3: 7; 4.4: 8
BASELINES | 2.2: Urban Network Baseline; 3.2: Precinct Baseline; 4.2: Project Concept Baseline 1; 4.3: Project Tender Baseline 2; 4.4: Project Construction Baseline 3
DELIVERABLES | Minutes of Engagement meetings | Work Plan | UN ID map | Council Submission | Terms of Reference | Urban Network Planning Plan | Updated Network Phasing Plan ( including High Order Costing ) | Precinct Design Plan | Precinct Phasing Plan and Precinct Concept Plan ( Spatial, High Level SDP and Phasing ) | Table of Prioritised Projects ( name, Scope, End Dates, Costing ) | Confirmation of Precinct Scope requirement. | Feasibility Study Reports | Tender Drawings, Documents and Costing from BoA | Contract Award | Delivered Construction Project with AS BUILT Drawings | Close-out Reports
| Institutional arrangement |  | Map description table | Council Resolution | Letter of Appointment |  | NDP Letter of Acceptance | NDP Letter of Acceptance |  |  | Project Execution Plan | Preliminary Design Drawings |  | Final Construction Phase Estimate
|  |  | Letter of NO Objection | MOA for NDP grant | SLA | [5 empty] | Agreement
Consultant Guidance Pack
Updated Work Plan
Approval / Acceptance by NDP | 1.2: Acceptance; 1.3: Letter of NO Objection; 1.4: Signing of MOA for NDP Grant; 1.5: Approval of Updated Work Plan; 2.2: NDP Letter of Acceptance; 3.1: NDP Letter of Acceptance; 3.2: NDP Approval Letter
REVIEWS | 3.2: Precinct Concept Review; 4.2: Preliminary Design review; 4.3: Critical Design Review
AUDITS | 3.1: From 1.3; 3.2: From 2.1; 3.3: From 3.2; 4.3: Functional; 4.5: Physical